## Coversheet
Report to the City Council pursuant to LL 18 of 2012
| Reporting Period: | FY20 Q4 (4/1/2020 to 6/30/2020)
| From: | Mayor's Office of Contract Services
Please find in "Section B" information on contracts required to be reported under Section B of LL 18 per the following criteria:
* Contracts registered with a maximum contract value of more than $10M,
* Connected with the capital budget,
* Having a contract modification registered in the reporting period,
* Current maximum contract value exceeds the maximum value from the time of registration by 20% or more.
Please find in "Section C" information on contracts required to be reported under Section C of LL 18 per the following criteria:
* Contracts registered with a maximum contract value of more than $10M,
* Connected with the capital budget,
* Maximum contract value exceeded the original by 20% or more as of the end of the last reporting period,
* Having a contract modification registered in the reporting period,
* Current maximum contract value exceeds the last reported value by 10% or more.

## Section B
AGENCY | CONTRACT ID | DESCRIPTION | VENDOR NAME | START DATE | END DATE | REG. DATE | ORIG. START DATE | ORIG. END DATE | ORIG. VALUE | MAX CONTRACT AMOUNT | PERCENTAGE INCREASE | Why did the maximum contract value increase more than 20% from the original value? | How many bidders submitted bids for the original contract?
DDC | CT185020040026358 | Reconstruction of Gateway Estates Area, Phase 1A | CAC INDUSTRIES INC | 2004-09-13 | 2008-03-31 | 2004-07-16 | 2004-06-30 | 2005-10-23 | 17445456.27 | 21256758.09 | 21% | The actual amount of work required to satisfactorily complete this project and to achieve its intent was more than what was anticipated in the Design stage. 1. The bid quantities for the removal of non-hazardous materials were lower than the actual quantities encountered in the field.The non-hazardous material existed in a larger area than originally anticipated. 2.The actual amount of contaminated soil encountered was more than anticipated. The original contract did not provide enough funds to remove and dispose of the contaminated materials. 3.The installation of sewer house connection work was not part of the original contract. The 22 new homes (ten on Flatlands Avenue and twelve on Vandalia Avenue) are on streets with existing sewer. HPD requested that DDC connect these houses to the existing sewers, because this work was not included in HPD’s contract with their builders. 4. The contract had no provision for the installation of house water services. Since the new homes have to be connected to the new water mains, additional fund was required to perform such work. This contract was substantially completed in 2008. DDC wasn't keeping electronic files at that time. Construction was contacted and they archived the contract. The information provided is based on what DDC was able to gather from different sources. During Phase 1A, DDC completed infrastructure work. Homes were built by HPD. | 3
DDC | CT185020131408317 | OCEAN BREEZE ATHLETIC CENTER | C&L CONTRACTING CORP | 2012-11-12 | 2016-08-09 | 2012-10-26 | 2012-11-15 | 2014-07-15 | 45086203.36 | 54509065.55 | 20% | The Additional registered change orders for the perforated panel CO 269 and CO 270 increased the contract value beyond the threshold. The originally designed panels had begun to rust due to interactions with salt water, and had to be redesigned by the architect. The change in materials and finishes in order to prevent rusting increased the costs of fabrication and installation for the panels. The Change order for the panels was anticipated however the exact cost could not be determined until the Architect of Record approved the materials and a mock up of the panels was provided by the contractor. When the mock up was approved in late 2019 the contractor was able to put together a proposal that included the manufacturer proposal in February 2020 for the panel fabrication. The CO was process and approved in April 2020. | 3
DDC | CTA185020177202221 | East Side Coastal Resiliency | AKRF-KSE JV | 2016-10-18 | 2020-08-27 | 2016-10-18 | 2016-10-20 | 2017-10-19 | 44088384 | 86075208 | 95% | During our value engineering exercise (as required by the federal funds on the project) it was decided by the city agencies involved to change direction in design to a raised park along with many other flood mitigation components. With the additional fill of raising the park, the existing outfalls and sewer infrastructure needed to be reconstructed to maintain the additional load anticipated for the project. This Design Task Order under the Design Requirements Contract, HWDRCW02, is to provide preliminary and final design services for the East Side Coastal Resiliency project in the Borough of Manhattan. The increase in design cost is due to the following reasons: 1) NYC DEP directed the design team to cease the design of the proposed storage tank in Project Area One and emergency pump station in Project Area Two. Instead, the team was directed to evaluate the feasibility, sizing, and siting study of a possible pump station in Project Area One. 2) Additional scope of services to provide interim cost analysis and cost reduction strategy support, to re-design a portion of the project and to develop alternative conceptual designs of the Houston Street punch-through, tennis courts, and East 6th Street areas of East River Park to achieve construction cost reduction. 3) City Team requested the consultant to develop the design of Tennis House Comfort Station and East 10th Street Comfort Station. NYC Parks requested the consultant to design additional maintenance area features, necessary to support their operations and maintenance needs with the project area. 4) Based on the study for alternative solutions to address interior drainage in Project Area One requested by NYC DEP, the interior drainage design was revised. The consultant was requested to design nine additional parallel conveyance lines. Additionally, the flood protection alignment, originally on East 25th Street, was revised to East 24th Street and a northern interceptor gate on East 20th Street. The revised alignment and gate location require the consultant to design an additional combined sewer system isolation gate at regulator M-39. 5) The consultant was directed to proceed with the raised park design alternative. This alternative shifts the flood protection alignment from the proposed alignment along the FDR Drive to along the East River esplanade, with the entirety of East River Park to be reconstructed behind this new raised waterfront edge. Additional scope of services includes the redesign of the flood protection system, bridges, and park design within East River Park to accommodate the raised park alternative. 6) NYC DEP directed the design team to design for upland tide gates at East 15th Street, East 16th Street and East 17th Street due to maintenance challenges and the benefit of eliminating the need to floodproof manholes on the FDR Drive. The original proposal was to install the tide gates on the bulkhead face. 7) Part of the interior drainage design was the development of a design concept for vertical slide gates. Due to operational and maintenance concerns associated with vertical slide gates, DEP requested the design team to evaluate the feasibility of a horizontal gate. Following initial evaluation, additional controls, power units and above-grade structures would be required for operation of horizontal swing gates. DDC and DEP directed the consultant to design the horizontal swing gates for interceptor gates and the associated structures and appurtenances. | 6
DEP | CT182620171423117 | Cleaning and Inspection, Queens and Brooklyn Tunnels | FRONTIER-KEMPER CONSTRUCTORS INC | 2017-05-27 | 2022-03-16 | 2017-05-24 | 2017-05-27 | 2018-08-19 | 22148600 | 39788372.56 | 79% | DEP directed Contract 542C to expedite the activation of City Tunnel No. 3, Stage 2 which in turn required Contract 542B to accelerate the tunnel cleaning and inspection. Contract 542B was expedited (along with 542C) to meet the Mayoral Directive of bringing City Tunnel No. 3, Stage 2 in Queens and Brooklyn into a state of activation readiness by January 2018, which was achieved. The site setup and shaft access preparation activities were also expedited. The contractor had to remove concrete cover slabs to gain access to Shaft 15B East as well as temporarily remove steel gratings and supporting steel beam. Additional funds were needed as the contractor exceeded the 300 Cubic Yards of material allowed in original contract to be removed, tested and disposed of. Extension of the contract required that security, guard services, maitenance of DEP field offices, trailer services, and temporary pest control services also be extended. DEP added the ability to add sodium hychlorite into City Tunnel No. 3 at Shaft 15B should DEP have the need for disinfection in the future. Additional funds were needed for shaft cap and flange coating repair. Funds were needed to address an existing leak at Shaft 15B as the leak flow increased from 30,000 gallons/day to 75,000 gallons/day. Finally, in order to meet the acceleration effort, additional funds were needed to compensate the contractor for working extending and additional 10 hr shifts, and working six days per week through lunch breaks and holidays so the vendor provided additional labor, supervisory staff, emergency medical technicians, site safety representatives, and needed travel and temporary housing for out-of-town staff. Additional equipment required: tunnel utility vehicles, spares as back-up equipment and modifications to the new equipment. This acceleration also added scope to the contract by requiring that the drainage sump be cleaned thereby increasing the amount of muck to be removed and increased mobilization/demobilization of pumping equipment and the maintenance of redundant and back-up pumping capacity. | 3
DOC | CT107220191402342 | As Needed General Contracting Services at Various DOC | AWL INDUSTRIES INC | 2018-09-01 | 2020-08-30 | 2018-09-25 | 2018-09-01 | 2020-08-30 | 12153300 | 15825840.15 | 30% | This contract was registered as a stop gap measure until the solicitation and registration of DOC's JOCS. However, due to significant delays with JOCS, the capacity of the general construction contract was increased for continued departmental services including new modular buildings and associated site work. JOCS was delayed due to specification revisions; terms and conations were added for the adjustment factors and award criteria used for calculating the JOCS bids. The procurement is currently with under review with NYC LAW. | 4

## Section C
AGENCY | CONTRACT ID | DESCRIPTION | VENDOR NAME | START DATE | END DATE | REG. DATE | ORIG. START DATE | ORIG. END DATE | ORIG. VALUE | LAST REPORTED AMOUNT | MAX CONTRACT AMOUNT | PERCENTAGE INCREASE | Why did the maximum contract value increase more than 10% from the last reported amount? | How many bidders submitted bids for the original contract?