## Coversheet
Report to the City Council pursuant to LL 18 of 2012
| Reporting Period: | FY21 Q4 (4/1/2021 to 6/30/2021)
| From: | Mayor's Office of Contract Services
Please find in "Section B" information on contracts required to be reported under Section B of LL 18 per the following criteria:
* Contracts registered with a maximum contract value of more than $10M,
* Connected with the capital budget,
* Having a contract modification registered in the reporting period,
* Current maximum contract value exceeds the maximum value from the time of registration by 20% or more.
Please find in "Section C" information on contracts required to be reported under Section C of LL 18 per the following criteria:
* Contracts registered with a maximum contract value of more than $10M,
* Connected with the capital budget,
* Maximum contract value exceeded the original by 20% or more as of the end of the last reporting period,
* Having a contract modification registered in the reporting period,
* Current maximum contract value exceeds the last reported value by 10% or more.

## Section B
AGENCY | CONTRACT ID | DESCRIPTION | VENDOR NAME | START DATE | END DATE | REG. DATE | ORIG. START DATE | ORIG. END DATE | ORIG. VALUE | MAX CONTRACT AMOUNT | PERCENTAGE INCREASE | Why did the maximum contract value increase more than 20% from the original value? | How many bidders submitted bids for the original contract?
DSNY | CT182720191421527 | CRS Floor Slab Rehabilitation. Emergency | IANNELLI CONSTRUCTION CO INC | 2019-01-14 | 2022-07-11 | 2019-04-23 | 2019-01-14 | 2020-05-14 | 11457000 | 17467451.56 | 52% | During the early days of the original CRS Slab replacement emergency and based on a scope of work that was provided to DSNY by our Engineering company, DSNY identified a need to replace large sections of the CRS Floor Slab which were displaying numerous stress fractures that raised concerns of an incomplete slab and infrastructure failure. This was also a health and safety issue for us. Due to the highly invasive nature of the work which was performed by our vendor, new fractures occurred in the areas adjacent to the work zone that was covered under the scope of work associated with the emergency. Once these new fractures were identified and analyzed by our engineering company (who classified them as severe and in need of immediate repair), it became apparent that there was a need to prevent the possibility of any additional areas collapsing due to the work being done in the adjoining areas of the floor slab that were in line with our original scope of work. Thus, the new fractures needed to be addressed expeditiously to prevent any additional infrastructure compromise and to prevent any additional costs that may have occurred had we waited to do this work at a later time (costs associated with new mobilizations and new permits.) As a result of this expansion, the contract value was increased. | 2
DDC | CT185020161423374 | INTERIOR RENOVATION AT 253 BROADWAY LANDMARKS PRESERVATION | E&A RESTORATION INC | 2016-07-01 | 2021-10-03 | 2016-06-10 | 2016-05-19 | 2017-11-10 | 24530000 | 33907335.45 | 38% | Increase to this project was due to several components or additions to this contract, which were all related to various field elements and conditions, considering the fact that this building is over 120 years old - Many these field conditions presented lots of challenges, plus decisions made by owner DCAS to address the change conditions, resulting in these increases. | 9
DOT | CT184120181400049 | TD+CSS: Replacement of Upper Roadways on the Queensboro Br. | THORNTON TOMASETTI INC | 2017-09-02 | 2022-01-12 | 2017-12-14 | 2017-09-02 | 2019-07-12 | 10182849.18 | 13058956.18 | 28% | A change order was requested to provide additional Design and CSS services, provided by Thornton Tomasetti, for the installation of Chain-link fence on the South Outer Roadway (SOR) of Queensboro Bridge project. These design and CSS tasks were not included in the original contract, and DOT had proposed to convert the SOR to a pedestrian walkway. In order to provide a safe environment for the traveling public, a security fence on the south (water side) of the SOR was need. This change order covered this work with all design and CSS tasks related. A change order was requested to provide additional work for fire stand pipe, CCTV and contract duration from 24 months to 54 month. | 7
DPR | CT184620201407412 | Reconstruction and Expansion of the Playground, Battery Park | PAUL J. SCARIANO INC | 2019-12-02 | 2021-03-30 | 2019-11-08 | 2019-12-02 | 2021-03-31 | 14904603 | 18085903.31 | 21% | An increase since original contract registration was due to a budget swap which temporarily increases the contract amount by $2,345,146.57. A contract action will be submitted for the decrease. The remaining $836,153.74 increase is due to change orders caused by design omissions and errors. Such design omissions included Drainage Pipe missed from the scope or incorrectly designed (3” DIP for Storage Room, 8” DIP for Storage Room to Street due to Designer Error, and 12” DIP due to broken line found underground during construction), Pavement missed from the scope, Minor work (Water Cap, MTA Waterproofing under Manhole, 2” Galvanized Conduit needed to encase Fog System Pipe, and Trailer), and removal/replacement of the DOT Boxes/Conduit due to the DOT. Construction is over 90% complete and the agency doesn't expect a significant contract increase due to change orders. | 4
DDC | CT185020181419023 | Construction of accelerated water main & sewer replacement | TRIUMPH CONSTRUCTION CORP | 2018-09-04 | 2020-06-15 | 2018-04-10 | 2018-07-01 | 2019-12-28 | 16951742.6 | 20421414.68 | 20% | An increase in the cost was due to several change orders as a result of field condition that have not been anticipated, including de-registration of remaining MTA Force Account Funding, the Shields Institute service connection, and stemming from the additional change orders a need for weekend work and night time premium time were needed. | 3

## Section C
AGENCY | CONTRACT ID | DESCRIPTION | VENDOR NAME | START DATE | END DATE | REG. DATE | ORIG. START DATE | ORIG. END DATE | ORIG. VALUE | LAST REPORTED AMOUNT | MAX CONTRACT AMOUNT | PERCENTAGE INCREASE | Why did the maximum contract value increase more than 10% from the last reported amount? | How many bidders submitted bids for the original contract?
DOITT | CT185820201424511 | COVID-19 EMERGENCY PURCHASE: EMERGENCY TECHNICAL SUPPORT | INTERNATIONAL BUSINESS MACHINES CORP | 2020-05-01 | 2023-04-30 | 2020-05-01 | 2020-05-01 | 2021-04-30 | 43702051 | 71450771 | 193863236.07 | 171% | The City of New York continues to have an urgent need for Technical Support Services to complete the critical enhancements and upgrades above that are already in progress as well as develop new tools and capabilities to help DoITT maintain the security, stability, and reliability of critical systems. This is crucial to support the City’s core operations throughout the remainder of the COVID-19 emergency and ensure the robust, resilient, and sustainable agency-integration and data-sharing ecosystem that will be needed for the City to rapidly recover from the emergency and thrive. The IBM team has the skill, knowledge, experience, governance, and agility necessary to assist DoITT in carrying out the remaining application development and management, data architecture, network and security services and preventive maintenance required. DoITT will therefore increase this Emergency Agreement and extend it by one year to ensure continuation and completion of critical initiatives commenced during the COVID-19 emergency. | Emergency Contract - Direct Award to IBM
DSBS | CTA180120207210111 | NYCF Barges PLI & Expansion 61550001 | NEW YORK CITY ECONOMIC DEVELOPMENT CORPORATION | 2015-07-15 | 2022-03-31 | 2020-07-30 | 2015-07-15 | 2022-03-31 | 19628733.11 | 32022270.86 | 37089057.95 | 15% | The increase in contract value for this project is a combination of several factors. The primary reason is the activation of additional fiscal years' funding for new project scopes through the approval of a CP amendments. Following the completion of the 2018/19 Ferry Feasibility Study, Mayor De Blasio announced that NYC Ferry will be expanding service to Staten Island’s St. George neighborhood, Manhattan’s West Side, Brooklyn’s Coney Island and Throgs Neck in the Bronx. As part of the expansion, new landings will be required at St. George, Coney Island Creek and Ferry Point Park. | 5