## Scheduled Completion 2021
Park's Contract # | FMS # | Property # | Project Title | Scope of Work | Contract Location | Borough | Construction SCD | Construction ACD | Final Inspection Date | Park Name | Contract Status
B007-118M | 846 P-211BNHT | B007 | Bensonhurst Park Playground Reconstruction | This project will reconstruct the playground, adjacent path system and sitting areas at the north end of Bensonhurst Park. | Cropsey Avenue between Bay Parkway and 21st Avenue | Brooklyn | 2020-09-07 | 2021-01-29 | 2020-12-30 | Bensonhurst Park | Completed
B008-118M | 846 P-216BHIP | B008 | Betsy Head Park Comfort Station Construction | This project will construct a comfort station at Imagination Playground in Betsy Head Park. | Bristol Street between Blake Avenue and Dumont Avenue | Brooklyn | 2021-06-01 | 2021-09-01 |  | Betsy Head Memorial Playground | Construction
B057-212MA | 846 P-2BRIGHM | B057 | Brigham Street New Park Construction | This project will construct a new playground to include play equipment, swings, spray shower area, hillside slide and a picnic area near Brigham Street in Marine Park. | Southeast corner of Brigham Street and Emmons Avenue | Brooklyn | 2020-05-04 | 2021-01-29 |  | Marine Park | Construction
B073-217MA | 846 P-2PPANEP | B073 | Prospect Park Vale of Cashmere Path Reconstruction | This project will reconstruct two sections of pathways in the Vale of Cashmere section of Prospect Park. | From the north side of the Endale Arch to the newly reconstructed path near the Zucker Natural Exploration area, and from Flatbush Avenue to the same reconstructed path | Brooklyn | 2021-08-30 |  |  | Prospect Park | Construction
B113-117M | 846 P-202CADM | B113A | Cadman Plaza Park Brooklyn War Memorial ADA Ramp and Elevator Construction | This project will install an accessible ramp and elevator at the Brooklyn War Memorial in Cadman Plaza Park. | Cadman Plaza West, Tillary Street, Cadman Plaza East, Tillary Street, Brooklyn Bridge | Brooklyn | 2021-01-11 | 2021-04-12 |  | S Parkes Cadman Plaza | Construction
B125-112M | 846 P-2PNYC05 | B125 | Calvert Vaux Park Comfort Station and Maintenance Facility Construction | This project will construct a comfort station and maintenance facility in Calvert Vaux Park. | Shore Parkway near Bay 48th Street | Brooklyn | 2021-05-24 | 2021-08-24 |  | Calvert Vaux Park | Construction
B223NC-118M | 846 P-2CPIPEN_PC-002323 | B223NC | Penn Triangle Reconstruction | This project will reconstruct Penn Triangle. | Penn Street, Wythe Avenue, Williamsburg Street East | Brooklyn | 2020-11-10 | 2021-01-09 | 2020-12-15 | Penn Triangle | Completed
BG-1018M | 846 P-2TRSD19_PC-002479 | NA | Brooklyn Tree-Damaged Sidewalk Reconstruction FY19 - Community Boards 1-6,8,9,14,16,17 | This project will reconstruct sidewalks damaged by adjacent city-owned trees in Brooklyn Community Boards 1-6, 8, 9, 14, 16, and 17. | Various locations in Brooklyn | Brooklyn | 2021-09-14 | 2021-09-14 |  | Multisite in Brooklyn | Construction
CNYG-1518M | 846 P-6TRSD19_PC-002638 | NA | Bronx and Manhattan Tree-Damaged Sidewalk Reconstruction FY19 | This project will reconstruct sidewalks damaged by adjacent city-owned trees in the Bronx and Manhattan. | Various locations in the Bronx and Manhattan |  | 2021-08-17 | 2021-08-17 |  | Multisite Citywide | Construction
M005-117M | 846 P-3BPPLGD | M005 | Battery Park Playground Reconstruction | This project will reconstruct and expand the playground at The Battery. | State Street and Peter Minuit Plaza | Manhattan | 2021-03-30 | 2021-05-30 |  | Battery Park | Construction
M017-216MA | 846 P-3LMDCCH | M017 | Corlears Hook Park Comfort Station Reconstruction | This project will reconstruct the comfort station at Corlears Hook Park. | Cherry Street between Jackson Street and FDR Drive | Manhattan | 2021-03-22 | 2021-06-22 |  | Corlears Hook Park | Construction
M047-118M | 846 P-3TOMJPK_PC-002267 | M047 | Thomas Jefferson Park Playground Reconstruction | This project will reconstruct Thomas Jefferson Playground. | East 114th Street between Pleasant Avenue and 1st Avenue | Manhattan | 2021-01-25 |  | 2021-01-08 | Thomas Jefferson Park | Completed
M056-118M | 846 P-309MPMP | M056 | Morningside Park Middle Playground and Basketball Courts Reconstruction | This project will reconstruct Middle Playground and the basketball courts at Morningside Park. | Morningside Drive and 118th Street | Manhattan | 2020-12-07 | 2021-03-05 |  | Morningside Park | Construction
M058-116M | 846 P-311MGLL | M058 | Marcus Garvey Park Comfort Station Construction | This project will construct a new comfort station and Little League building in Marcus Garvey Park. | 18 Mount Morris Park West, between West 121st Street and West 122nd Street | Manhattan | 2019-01-29 | 2021-03-30 |  | Marcus Garvey Memorial Park | Construction
M108-116MA1 | 846 P-308SPCS | M108Q | Twenty-Four Sycamores Park Comfort Station Reconstruction | This project will reconstruct the comfort station at Twenty-Four Sycamores Park. | FDR Drive, East 60th Street, East 61st Street, York Avenue | Manhattan | 2021-05-04 | 2021-08-04 |  | Twenty-Four Sycamores Park | Construction
M159-219M | 846 P-3CPIFJP_PC-002750 | M159 | Frederick Johnson Playground Play Area Reconstruction | This project will reconstruct the play area at Frederick Johnson Playground. | Adam Clayton Powell Jr. Boulevard (7th Avenue) between West 150th Street and West 151st Street | Manhattan | 2021-07-31 |  |  | Frederick Johnson Park | Construction
M165A-116M | 846 P-303BPCS | M165 | Baruch Playground Comfort Station Reconstruction | This project will reconstruct the comfort station at Baruch Playground. | Baruch Place and Rivington Street | Manhattan | 2020-01-27 | 2021-04-30 |  | Baruch Playground | Construction
M167-118M | 846 P-301PECK | M167 | Peck Slip Reconstruction | This project will reconstruct Peck Slip. | Peck Slip between Water Street and South Street | Manhattan | 2021-01-25 |  | 2021-01-25 | Peck Slip | Completed
M193-117MA | 846 P-3CPI3AL | M193 | Abraham Lincoln Playground Reconstruction | This project will reconstruct Abraham Lincoln Playground. | Fifth Avenue and East 135th Street | Manhattan | 2021-09-11 |  |  | Lincoln Playground | Construction
M193-217M | 846 P-3CPI3A2 | M193 | Abraham Lincoln Playground Comfort Station Reconstruction | This project will reconstruct the comfort station in Abraham Lincoln Playground. | Fifth Avenue and East 135th Street | Manhattan | 2021-03-01 | 2021-06-01 |  | Lincoln Playground | Construction
M240-218MA | 846 P-3CPI3AC_PC-002237 | M240 | Audubon Playground Comfort Station Reconstruction | This project will reconstruct the comfort station at Audubon Playground and make it ADA accessible. | Audubon Avenue between West 169th Street and West 170th Street | Manhattan | 2021-04-04 |  |  | Audubon Playground | Construction
M259-118M | 846 P-303MCKY | M259 | McKinley Playground Play Area Reconstruction | This project will reconstruct the playground and spray shower, including fencing, paving, curbs, safety surfacing, benches, lighting, play equipment, plantings, and trees at McKinley Playground. | East 3rd Street, East 4th Street, Avenue A, 1st Avenue | Manhattan | 2021-09-13 |  |  | McKinley Playground | Construction
Q004-318M | 846 P-4ANCH03_PC-002425 | Q004 | Astoria Park Charybdis Playground Reconstruction and Spray Shower Construction | This project will reconstruct Charybdis Playground and construct a spray shower in Astoria Park. | Between Shore Boulevard and 19th Street at 23rd Road | Queens | 2021-03-22 | 2021-06-21 |  | Astoria Park | Construction
Q004-418M | 846 P-4ANCH04_PC-002426 | Q004 | Astoria Park Charybdis Playground Comfort Station Reconstruction | This project will reconstruct the comfort station at Charybdis Playground in Astoria Park. | Between Shore Boulevard and 19th Street at 23rd Road | Queens | 2021-08-16 | 2021-11-16 |  | Astoria Park | Construction
Q020-118M | 846 NDF-HLDN5_PC-002342 | Q020 | Highland Park Pedestrian Paths and Sidewalks Reconstruction | This project will reconstruct the sidewalk and improve pedestrian access along a portion of Highland Boulevard. | Highland Boulevard between Jamaica Avenue and Vermont Place | Queens | 2021-09-20 |  |  | Highland Park | Construction
Q023-216MA | 846 P-412RK01 | Q023 | Rufus King Park Entrance Construction and Fence Reconstruction | This project will reconstruct the perimeter fence and passive recreation area at Rufus King Park. | Jamaica Avenue between 150th and 153rd Streets | Queens | 2021-05-11 |  |  | Rufus King Park | Construction
Q031A-118M | 846 P-402DBOY_PC-002306 | Q031A | Doughboy Plaza Seating Area Reconstruction | This project will reconstruct the seating area surrounding the monument at Doughboy Plaza, including the drinking fountain and pathways. | Woodside Avenue between 54th Street and 56th Street | Queens | 2021-09-20 |  |  | Doughboy Plaza | Construction
Q067-117MA | 846 P-402HART | Q067A | General Hart Playground Reconstruction | This project will reconstruct General Hart Playground, including play equipment, swings, spray shower, basketball courts, planting, pavement, fencing, and benches. | 37th Avenue, 65th Street, 69th Street, Broadway | Queens | 2021-01-04 | 2021-03-18 | 2020-11-09 | General Hart Playground | Completed
Q099-808MA1 | 846 P-4OLMST4 | Q099 | Olmsted Center Reconstruction | This project will reconstruct the Olmsted Center in Flushing Meadows Corona Park. | 117-02 Roosevelt Avenue | Queens | 2016-10-31 | 2021-04-30 |  | Flushing Meadows Park | Construction
Q099-817MA | 846 P-415LWCS_PC-002198 | Q099 | Flushing Meadows Corona Park Lawrence Playground Comfort Station Reconstruction | This project will reconstruct the comfort station at Lawrence Playground in Flushing Meadows Corona Park. | Van Wyck Expressway, Botanical Garden Bridge, College Point Boulevard | Queens | 2021-03-08 |  |  | Flushing Meadows Park | Construction
Q205B-118M | 846 P-4LTLBSH | Q205B | Little Bush Park Playground Reconstruction | This project will reconstruct the playground at Little Bush Park. | Laurel Hill Boulevard between 63rd Street and 64th Street | Queens | 2021-09-07 |  |  | Nathan Weidenbaum Park | Construction
Q310-118M | 846 P-4GLNOAK | Q310 | Glen Oaks Oval Playground Reconstruction and Adult Fitness Equipment Construction | This project will reconstruct the playground and replace the basketball court with an adult fitness equipment area at Glen Oaks Oval. | 260th Street and 74th Avenue | Queens | 2021-09-14 |  |  | Glen Oaks Oval | Construction
QG-1018M | 846 P-4TRSD19_PC-002478 | NA | Queens Tree-Damaged Sidewalk Reconstruction FY19 - Community Boards 1-7,9,10 | This project will reconstruct sidewalks damaged by adjacent city-owned trees in Queens Community Boards 1-7, 9, and 10. | Various locations in Queens | Queens | 2021-07-27 | 2021-07-27 |  | Multisite in Queens | Construction
QG-1118M | 846 P-4TRS19A_PC-002636 | NA | Queens Tree-Damaged Sidewalk Reconstruction FY19 - Community Boards 8,11-14 | This project will reconstruct sidewalks damaged by adjacent city-owned trees in Queens Community Boards 8 and 11-14. | Various locations in Queens | Queens | 2021-09-21 | 2021-09-21 |  | Multisite in Queens | Construction
R017-115M | 846 P-5FRESH9 | R017 | Freshkills North Park Pathway and Comfort Station Construction | This project will construct a new multi-use pathway, overlook structures, and comfort station with composting toilets in the northern section of Freshkills Park. | Dean Avenue, West Shore Expressway, Fresh Kills and Main Creek | Staten Island | 2020-01-05 | 2021-06-30 |  | Fresh Kills Park | Construction
R061-116M | 846 P-5CPISTP | R061 | Rev. Dr. Maggie Howard Playground Reconstruction | This project will reconstruct the playground, multi-use fields, basketball and handball courts, and water features at Rev. Dr. Maggie Howard Playground. | Tompkins Avenue between Broad Street and Hill Street | Staten Island | 2020-03-20 | 2021-04-16 |  | Stapleton Playground | Construction
R067-117M | 846 SANDY5-45 | R067 | MacArthur Park Multi-Purpose Ballfield and Basketball Court Reconstruction | This project will reconstruct the existing ballfields, basketball courts, and sports lighting, and improve the edges and entrances at MacArthur Park. | Jefferson Street between Dongan Hills Avenue and Seaver Avenue | Staten Island | 2020-10-13 | 2021-02-16 |  | MacArthur Park | Construction
R072-117MA | 846 P-5CLAWS | R072 | Clawson Playground Reconstruction Phase I | This project will reconstruct the area of Clawson Playground behind PS 50 with new play equipment, safety surfacing, benches and plantings. | Adelaide Avenue betweeen Elmira Street and Whitehall Street | Staten Island | 2021-03-08 | 2021-05-07 | 2020-10-02 | Clawson Playground (PS 50) | Completed
R085-118M | 846 P-5PRESPL_PC-002251 | R085 | Prescott Playground Reconstruction | This project will reconstruct Prescott Playground, including fencing, retaining walls, play equipment, and pavements. | Irvington Street and Edith Avenue | Staten Island | 2021-01-11 | 2021-04-12 |  | E.M.T. Christopher J. Prescott Playground | Construction
R089-115M | 846 P-503GCPL | R089 | Greencroft Playground Comfort Station Construction | This project will demolish the existing comfort station and construct a new comfort station at Greencroft Playground. | Greencroft Avenue Between Redgrave Avenue and Ainsworth Avenue | Staten Island | 2021-06-01 | 2021-09-01 |  | Greencroft Playground | Construction
R125-118M | 846 P-5LILOPL_PC-002253 | R125 | Lopez Playground Reconstruction | This project will reconstruct Lopez Playground. | Palma Drive between Targee Street and Oder Avenue | Staten Island | 2021-05-31 | 2021-07-30 |  | Luiz Lopez Playground | Construction
R153-118M | 846 SANDY5-50_PC-002219 | R153 | Fairview Park Multi-Purpose Field and Landscape Construction | This project will construct a multi-purpose field, baseball field, tennis courts, pickleball courts, adult fitness equipment, picnic area, parking area, bio-retention areas, paths, and landscape elements at Fairview Park. | Arthur Kill Road and Veterans Road West | Staten Island | 2020-08-04 | 2021-01-31 |  | Fairview Park | Construction
R153-218M | 846 SANDY5-49_PC-002216 | R153 | Fairview Park Comfort Station Construction | This project will construct a new comfort station at Fairview Park. | Bricktown Way between Arthur Kill Road & Veterans Road West | Staten Island | 2021-09-27 |  |  | Fairview Park | Construction
RG-418M | 846 P-5TRSD19_PC-002477 | NA | Staten Island Tree-Damaged Sidewalk Reconstruction FY19 | This project will reconstruct sidewalks damaged by adjacent city-owned trees in Staten Island. | Various locations in Staten Island | Staten Island | 2021-07-20 | 2021-07-20 |  | Multisite in Staten Island | Construction
X010-114M | 846 P-1CRNAPK | X010 | Crotona Park Nature Center Reconstruction | This project will reconstruct the nature center in Crotona Park. | Crotona Avenue and Crotona Park East | The Bronx | 2019-09-09 | 2021-01-29 |  | Crotona Park | Construction
X010-210MA3 | 846 P-1CRPOHS | X010 | Crotona Park Bathhouse Entrance Reconstruction | This project will reconstruct the entrance towers, mezzanine roof and bridge at the entrance to the Crotona Park Bathhouse. | Fulton Avenue and East 173rd Street | The Bronx | 2019-12-02 | 2021-02-01 |  | Crotona Park | Construction
X010-214MA1 | 846 P-103CRCS | X010 | Crotona Park Comfort Station Reconstruction | This project will reconstruct the comfort station at Playground of the Stars in Crotona Park. | Franklin Avenue and Crotona Park South | The Bronx | 2021-03-23 | 2021-06-23 |  | Crotona Park | Construction
X017-117MA | 846 P-1ECHOPK | X017 | Echo Park Playground and Basketball Courts Reconstruction | This project will reconstruct the playground, spray shower, and basketball courts at Richman (Echo) Park. | Valentine Avenue between East Tremont and East Burnside Avenues | The Bronx | 2021-02-22 |  |  | Julius Richman Park | Construction
X045-218M | 846 P-1ANCH02_PC-002291 | X045 | St. Mary's Park Amphitheater, Plaza, and Pathways Reconstruction | This project will reconstruct the amphitheater, plaza, pathways and lighting at St. Mary's Park. | St. Anns Avenue between East 143rd Street and East 149th Street | The Bronx | 2021-09-21 |  |  | St. Mary's Park | Construction
X138-117MA | 846 P-1CPI134 | X138 | Playground 134 Reconstruction | This project will reconstruct Playground 134 with new basketball courts, play equipment, a skate park, adult fitness equipment, a spray shower, and swings. | East 133rd Street, St. Anns Place, East 134th Street, Cypress Avenue | The Bronx | 2021-04-19 | 2021-06-28 |  | Playground One Thirty Four CXXXIV | Construction
X148A3-318M | 846 NDF-BRPLG_PC-002665 | X148A3 | Bridge Playground Reconstruction | This project will reconstruct Bridge Playground. | Boscobel Place, Undercliff Avenue, University Avenue | The Bronx | 2021-09-13 |  |  | Bridge Playground | Construction
X148H1-118M | 846 P-1CPIPRO | X148H1 | Prospect Playground Reconstruction | This project will reconstruct Prospect Playground. | East 176th Street between Clinton Avenue and Prospect Avenue | The Bronx | 2021-09-27 |  |  | Prospect Playground | Construction
X163-118M | 846 P-111LRTO | X163 | Loreto Playground Asphalt Multi-Purpose Play Area Construction | This project will construct an expanded asphalt multi-purpose play area in Loreto Playground. | Morris Park Avenue, Tomlinson Avenue, Haight Avenue, and Van Nest Avenue | The Bronx | 2021-09-07 |  |  | Loreto Playground | Construction