## 2019
Parks' Contract # | Short Description | Contract Summary | Contract Location | Borough | Construction SCD | Construction ACD | Park Name | Contract Status
B245-111M | St. John's Recreation Center Comfort Station Construction | This project will construct a comfort station adjacent to the St. John's Recreation Center. | Prospect Place between Troy Avenue and Schenectady Avenue | Brooklyn | 2016-03-01 | 2019-01-31 | St. John's Recreation Center | Construction
B109-112M | Bill Brown Playground Comfort Station Reconstruction | This project will reconstruct the comfort station in Bill Brown Playground. | Bedford Avenue, Avenue X, Avenue Y, East 24th Street | Brooklyn | 2016-08-15 | 2019-03-29 | Bill Brown Memorial Playground | Construction
X004-213M | Bronx River Park 233rd Street Bikeway Reconstruction | This project will reconstruct the paths, landscape and staircase at East 233rd Street in Bronx River Park. | East 233rd Street and the Bronx River | Bronx | 2018-01-24 | 2019-05-15 | Bronx River Parkway | Construction
X001-207MA2 | Aqueduct Walk 182nd Street Comfort Station Construction | This project will construct a comfort station in Aqueduct Walk. | Aqueduct Avenue East between West 182nd Street and West 183rd Street | Bronx | 2018-03-12 | 2019-03-15 | Aqueduct Walk | Construction
B395-115MA1 | Green Central Knoll Comfort Station Construction | This project will construct a new comfort station and an accessible ramp in Green Central Knoll. | Evergreen Avenue and Knoll Street | Brooklyn | 2018-06-18 | 2019-05-31 | Green Central Knoll | Construction
M108-113M | Sutton Place Park Reconstruction | This project will reconstruct a portion of Sutton Place Park. | FDR Drive between 56th and 57th Streets | Manhattan | 2018-06-18 | 2019-06-17 | Sutton Place Park | Construction
X169-114M | Agnes Haywood Playground Reconstruction | This project will reconstruct Agnes Haywood Playground. | Barnes Avenue between East 215th Street and East 216th Street | Bronx | 2018-07-09 | 2019-03-22 | Agnes Haywood Playground | Completed
M058-115M | Marcus Garvey Park Fire Watchtower Restoration | This project will reconstruct the fire watchtower and surrounding plaza in Marcus Garvey Park. | Madison Avenue at East 122nd Street | Manhattan | 2018-07-09 | 2019-04-20 | Marcus Garvey Memorial Park | Construction
X113-115MA | Hunts Point Playground Reconstruction | This project will reconstruct the play equipment, safety surfacing, spray shower, fencing, benches and landscaping in Hunts Point Playground. | Spofford Avenue Between Faile Street and Hunts Point Avenue | Bronx | 2018-08-27 | 2019-03-29 | Hunts Point Playground | Construction
M353-112M | Riverside Park South Playground, Bikeway, and Plazas Construction | This project will construct a portion of Riverside Park South between West 65th Street and West 68th Street, including new plazas, play areas, lawns, volleyball courts, and a dog run, and it will reconstruct the bikeway between West 62nd Street and West 70th Street. | Riverside Boulevard between West 62nd Street and West 70th Street | Manhattan | 2018-08-28 | 2019-08-27 | Riverside Park South | Construction
CNYG-3215M | Luther Gulick, Lyons Square, Saw Mill, Melrose Commons and Ten Eyck Playgrounds Comfort Station Construction | This project will construct comfort stations at various locations in Brooklyn, the Bronx, and Manhattan. | Ten Eyck Playground, Brooklyn; Lyons Square Playground, Bronx; Melrose Commons Playground, Bronx; Saw Mill Playground, Bronx; Luther Gulick Playground, Manhattan |  | 2018-08-30 | 2019-02-15 | Multisite Citywide | Construction
B118-116M | St. Mary's Playground Multi-Purpose Area Reconstruction | This project will reconstruct the existing multipurpose play area at St. Mary's Playground to include a skate park, basketball courts, multi-use synthetic turf field, adult fitness equipment and color seal coat walking track. | Smith Street between Nelson Street and Luquer Street | Brooklyn | 2018-10-01 | 2019-06-28 | St. Mary's Playground | Construction
RG-515MA1 | Arrochar Playground and Grandview Playground Comfort Station Reconstruction | This project will reconstruct the comfort stations at Arrochar Playground and Grandview Playground. | Various locations in Staten Island | Staten Island | 2018-10-17 | 2019-01-31 | Multisite in Staten Island | Completed
RG-216MA | Levy Playground, McDonald Park and DeMatti Playground Comfort Station Reconstruction | This project will reconstruct three comfort stations at various locations in Staten Island. | Levy Playground, 133 Jewett Ave, Staten Island; McDonald Playground, east of Broadway, between Myrtle and Forest Avenues, Staten Island; DeMatti Playground, 430 Tompkins Ave, Staten Island | Staten Island | 2018-10-24 | 2019-04-05 | Multisite in Staten Island | Construction
BG-815MA | Jesse Owens, Stockton and Stroud Playgrounds Comfort Station Reconstruction | This project will reconstruct the comfort stations Jesse Owens Playground, Stockton Playground, and Stroud Playground. | Various locations in Brooklyn | Brooklyn | 2018-12-19 | 2019-04-19 | Multisite in Brooklyn | Construction
B350-115MA | Stroud Playground Reconstruction | This project will reconstruct the playground, multi-use area, landscaping, play equipment, safety surface, spray shower, seating areas, basketball court and handball court at Stroud Playground. | Stroud Playground West of Classon Avenue Between Park Place and Sterling Place. | Brooklyn | 2019-01-15 |  | Stroud Playground | Completed
R006-213M | Conference House Pavilion Reconstruction | This project will reconstruct the Conference House Pavilion in Conference House Park. | Conference House Park at the End of Hylan Boulevard, Adjacent to Satterlee Street, Borough of Staten Island | Staten Island | 2019-01-21 | 2019-10-21 | Conference House Park | Construction
M058-116M | Marcus Garvey Park Comfort Station Construction | This project will construct a new comfort station and Little League building in Marcus Garvey Park. | 18 Mount Morris Park West, between West 121st Street and West 122nd Street | Manhattan | 2019-01-29 | 2019-08-15 | Marcus Garvey Memorial Park | Construction
QG-416M | Queens Roller Hockey Rinks Reconstruction | This project will reconstruct roller hockey rinks at Juniper Valley Park, Harvey Park, Mafera Park and College Point Park. | Locations include Juniper Valley Park, Harvey Park, Mafera Park, and College Point Park | Queens | 2019-02-20 |  | Multisite in Queens | Completed
X104-115M | Williamsbridge Oval Skate Park Construction | This project will construct a new skate park at Williamsbridge Oval. | Reservoir Oval East between Holt Place and Reservoir Place | Bronx | 2019-02-25 | 2019-05-15 | Williamsbridge Oval | Construction
Q308-115M | Bowne Playground Reconstruction | This project will reconstruct the playground, asphalt field, seating area and swings at Bowne Playground. | Sanford Ave between Union Street and Barclay Ave | Queens | 2019-02-28 |  | Bowne Playground | Completed
X287-116M | Ogden Plimpton Playground Reconstruction | This project will reconstruct Ogden Plimpton Playground. | Plimpton Avenue between West 170th Street and Edward L Grant Highway. | Bronx | 2019-03-04 |  | Ogden Plimpton Playground | Completed
B068-115MA | Parade Ground Ballfield 7 Reconstruction and Adult Fitness Construction | This project will construct seven new adult fitness equipment stations, a misting station, trees and benches, and reconstruct the synthetic turf field at Ballfield 7 at the Parade Ground. | Near Caton Avenue and Stratford Road | Brooklyn | 2019-03-04 |  | Parade Ground | Completed
B087-216M | Sunset Park Adult Fitness Area Construction | This project will construct an adult fitness area in Sunset Park. | 41st Street at 6th Avenue | Brooklyn | 2019-03-04 |  | Sunset Park | Completed
B054-116M | Lincoln Terrace Park Playground Reconstruction | This project will reconstruct play equipment for 2-5 and 5-12 years old, swings, spray shower, a seating area for general public, benches, lighting, fencing, drainage, water supply systems and plantings in Lincoln Terrace Park. | The playground is located on Rochester Avenue between President street and Carroll street, borough of Brooklyn | Brooklyn | 2019-03-04 |  | Lincoln Terrace Park / Arthur S. Somers | Completed
M056-116M | Morningside Park 123rd Street Playground Reconstruction Phase 2 | This project will reconstruct the play equipment, seating, planting, lighting, pavements, fencing, and drainage and water supply systems at 123rd Street Playground in Morningside Park. | West 123rd Street and Morningside Avenue | Manhattan | 2019-03-04 |  | Morningside Park | Completed
QG-1613MA | Queens General Comfort Station and Facility Reconstruction (QG-1613MA) | This project will reconstruct comfort stations and facilities at various parks and recreation locations in Queens. | Various locations, Queens | Queens | 2019-03-05 |  | Multisite in Queens | Completed
Q099-113M | Flushing Meadows Corona Park Meadow Lake Promenade Reconstruction | This project will reconstruct the roadway and paths along the Meadow Lake Promenade. | Flushing Meadows Corona Park, Meadow Lake Promenade between the Boathouse Bridge and the Ederle site | Queens | 2019-03-10 |  | Flushing Meadows Corona Park | Construction
Q020-116MA | Highland Park Basketball Courts Reconstruction | This project will reconstruct four basketball courts in Highland Park. | Jamaica Avenue at Cleveland Street | Queens | 2019-03-11 |  | Highland Park | Completed
Q446-116MA | Sorrentino Recreation Center Reconstruction | This project will reconstruct portions of Sorrentino Recreation Center. | 18-48 Cornaga Avenue | Queens | 2019-03-14 |  | Sorrentino Recreation Center | Completed
Q458-116M | Bayside Historical Society Officers Club Porch Reconstruction | This project will reconstruct the front portico at the Bayside Historical Society Officers Club in Fort Totten Park. | 208 Totten Avenue | Queens | 2019-03-18 |  | Fort Totten Park | Completed
M237-116M | Seravalli Playground Comfort Station Reconstruction | This project will reconstruct the comfort station at Seravalli Playground. | Corporal John A. Seravalli Playground located on Hudson Street between Gansevoort Street and Horatio Street. | Manhattan | 2019-03-19 |  | Corporal John A. Seravalli Playground | Construction
M104-116M | Randall's Island Western Shore Reconstruction | This project will reconstruct a portion of the western shore on Randall's Island. | Randall's Island, Harlem River | Manhattan | 2019-03-20 |  | Randall's Island Park | Completed
B541-115M | Gateway Estates Phase 1 Playground and Comfort Station Construction | This project will construct a playground and comfort station at Gateway Estates. | Vandalia Avenue and Berriman Street, Erskine Street and Schroeders Avenue | Brooklyn | 2019-03-26 |  | Berriman Park (Unofficial Name) | Completed
X205-116M | Black Rock Playground Reconstruction | This project will reconstruct the playground at Black Rock Playground. | Watson Avenue, Black Rock Avenue between Virginia Avenue and Pugsley Avenue | Bronx | 2019-03-29 |  | Black Rock Playground | Completed
Q123-116M | Astoria Health Playground Reconstruction | This project will reconstruct Astoria Health Playground. | 14th Street between 31st Avenue and 31st Drive | Queens | 2019-03-29 |  | Astoria Health Center Playground | Completed
Q066-116M | Triborough Bridge Playground C Reconstruction | This project will construct a dog run and reconstruct a basketball court at Triborough Bridge Playground C. | Hoyt Avenue North, Hoyt Avenue South, 23rd Street, 24th Street | Queens | 2019-04-01 |  | Triborough Bridge Playground C | Completed
QG-1513MA1 | Queens General Comfort Station and Facility Reconstruction (QG-1513MA1) | This project will reconstruct comfort stations and facilities at various parks and recreation locations in Queens. | Various locations, Queens | Queens | 2019-04-09 |  | Multisite in Queens | Completed
B324-116M | Jacob Joffe Fields Adult Fitness Area Construction and Sport Courts Reconstruction | This project will reconstruct the basketball and handball courts at Jacob Joffe Fields. | Avenue K between 58th Street and 59th Street | Brooklyn | 2019-04-15 |  | Joffe Park | Completed
R016-115M | New Dorp Beach Site Restoration in Great Kills Park (Hurricane Sandy) | This project will reconstruct Hurricane Sandy-damaged site amenities, a spray shower and paths at New Dorp Beach in Great Kills Park. | Ebbits Avenue and New Dorp Lane along Cedar Grove Avenue | Staten Island | 2019-04-15 |  | Great Kills Park | Completed
B099-116M | Lt. Joseph Petrosino Park Reconstruction | This project will reconstruct Lt. Joseph Petrosino Park. | 70th Street, 16th Avenue, 71st Street, New Utrecht Avenue | Brooklyn | 2019-04-23 |  | Lt. Petrosino Playground | Completed
QG-316M | Laurelton Playground and Bayswater Park Skate Elements and Seating Areas Construction | This project will provide skate park elements and related site amenities at Laurelton Playground and Bayswater Park. | Various locations in Queens | Queens | 2019-04-27 |  | Multisite in Queens | Completed
Q106-113MD | O'Connell Playground Recreation Building Reconstruction | This project will reconstruct the recreation building in Daniel M. O'Connell Playground. | Murdoch Avenue, 113th Avenues, 196th Street, 197th Street | Queens | 2019-04-29 |  | Daniel M. O'Connell Playground | Construction
B038-116M | Fulton Park Comfort Station Reconstruction | This project will reconstruct the comfort station at Fulton Park. | Stuyvesant Avenue between Chauncey and Fulton Streets | Brooklyn | 2019-05-03 |  | Fulton Park | Construction
M042-117M | Inwood Hill Park Adult Fitness Equipment Construction | This project will construct adult fitness equipment in Inwood Hill Park. | North of Dyckman Street near the Hudson River | Manhattan | 2019-05-13 |  | Inwood Hill Park | Completed
B429-116M | Hope Ballfield Reconstruction | This project will reconstruct the baseball field, outdoor gym, playground, sitting area and perimeter sidewalks at Hope Ballfield. | Knickerbocker Avenue between Menahan and Grove Streets | Brooklyn | 2019-05-13 |  | Hope Ballfield | Construction
Q218-116M | Dutch Kills Playground and Court Area Reconstruction | This project will reconstruct the playground and court area in Dutch Kills Playground. | Crescent Street, 28th Street, 36th Avenue, 37th Avenue | Queens | 2019-05-13 |  | Dutch Kills Playground | Construction
R129-116M | Staten Island Greenbelt Recreation Center Parking Area Expansion | This project will expand the parking area at Greenbelt Recreation Center. | West of Brielle Avenue between Rockland and Walcott Avenues. | Staten Island | 2019-05-13 |  | Blood Root Valley | Construction
Q296-116M | Playground Thirty Five XXXV Reconstruction | This project will reconstruct Playground Thirty Five XXXV. | 35th Avenue between Steinway Street and 41st Street | Queens | 2019-05-20 |  | 35 Playground | Construction
CNYG-814MA | Citywide Comfort Station and Facility Reconstruction (CNYG-814MA) | This project will reconstruct comfort stations and facilities at various parks and recreation locations citywide. | Various locations, citywide |  | 2019-05-22 |  | Multisite Citywide | Construction
Q099-517M | World's Fair Playground Asphalt Field Reconstruction | This project will reconstruct the asphalt field at World's Fair Playground in Flushing Meadows Corona Park. | along the Grand Central parkway near 62nd road in the Borough of Queens | Queens | 2019-06-03 |  | Flushing Meadows Park | Construction
X147-111M | Starlight Park Comfort Station Construction |  |  | Bronx | 2019-06-05 |  | Starlight Park | Design
X002-116M | Bronx Park Dog Run Construction | This project will construct a dog run in Bronx Park, west of the intersection of Bronx Park East and Boston Road. | Bronx Park East and Boston Road | Bronx | 2019-06-10 |  | Bronx Park | Construction
R006-114M | Conference House Park Path, Rail, and Landscape Reconstruction (Hurricane Sandy) | This project will reconstruct Hurricane Sandy-damaged paths, the overlook and the parking lot in Conference House Park. | Page Avenue between Raritan Bay and Hylan Boulevard | Staten Island | 2019-06-17 |  | Conference House Park | Completed
BG-38500-113M | Beaver Noll Park Construction | This project will construct Beaver Noll Park, which will include a tot lot and sitting area. | Bushwick Avenue and Beaver Street | Brooklyn | 2019-06-17 |  | Beaver Noll Park | Construction
M071-116M | Riverside Park Path Reconstruction, West 72-83, 91-95, 122-125 Streets | This project will include paving and landscape improvements in Riverside Park. At Riverside Drive between West 122nd and West 125th Streets, the project will reconstruct the existing perimeter sidewalk, including asphalt pavement and new bluestone curb, benches and fencing. At Crabapple Grove between West 91st and West 95th Streets, the project will reconstruct park paths and install new benches. Along the Hudson River Greenway between West 72nd and West 83rd Streets, the project will install additional greenway signage, improve park lighting and reconstruct pavements. | Riverside Drive: West 125th-122nd Streets, West 95th-91st Streets, West 83rd-72nd Streets | Manhattan | 2019-06-17 |  | Riverside Park | Construction
Q099-717M | Flushing Meadows Corona Park Lawrence Playground Reconstruction | This project will reconstruct Lawrence Playground in Flushing Meadows Corona Park. | Bounded by the Van Wyck Expressway, Botanical Garden Bridge and College Point Boulevard, Borough of Queens | Queens | 2019-06-17 |  | Flushing Meadows Park | Construction
Q163-215M | Sandpiper Playground Reconstruction | This project will reconstruct Sandpiper Playground. | On Shore Front Parkway between Beach 105th Street and Beach 108th Street at Rockaway Beach, Borough of Queens. | Queens | 2019-06-17 |  | Rockaway Beach & Boardwalk | Construction
BG-715MA | Brooklyn General Site Work (BG-715MA) | This project will reconstruct the play equipment, safety surfacing, handball courts, basketball courts, pavements, fencing, site plumbing and general site work at various parks in Brooklyn. | Various locations in Brooklyn. | Brooklyn | 2019-06-18 |  | Multisite in Brooklyn | Construction
X045-215MA | St. Mary's Park Playground West Reconstruction | This project will reconstruct the basketball and tennis courts, and install play equipment, seating areas, planting beds and trees at St. Mary's Park Playground West. | St Anns Ave, East 149 St and St Mary's Recreation Center | Bronx | 2019-06-28 |  | St. Mary's Playground | Construction
B141-116M | City Line Park Synthetic Turf Field, Skate Park, and Basketball Court Construction | This project will convert the existing asphalt athletic field at City Line Park into a multipurpose active recreation area to include a synthetic turf field, skate park, basketball court, adult fitness equipment and other site amenities. | Fountain Avenue, Welden Street, McKinley Avenue | Brooklyn | 2019-07-08 |  | City Line Park | Construction
M029-116M | Jacob Javits Playground Reconstruction | This project will reconstruct the playground, basketball court, drainage and water supply systems and surrounding landscape, and construct new adult fitness equipment in Jacob Javits Playground. | The playground is located at Margaret Corbin Plaza between Cabrini Boulevard and Fort Washington Avenue. | Manhattan | 2019-07-08 |  | Fort Tryon Park | Construction
Q020-216M | Highland Park Lower Western Playground Reconstruction | This project will reconstruct the Western Lower Highland Playground to include play equipment and seating areas. | Playground West of the Comfort Station in Lower Highland Park on Jamaica Avenue Between Elton and Cleveland Streets | Queens | 2019-07-08 |  | Highland Park | Construction
QG-216M | Queens Athletic Courts Reconstruction (QG-216M) | This project will reconstruct tennis, basketball and handball courts in Baisley Pond Park; basketball courts and an entry ramp at Police Officer Nicholas Demutiis Playground; and basketball and handball courts at Harvard Playground in Queens. | This project will reconstruct tennis, basketball and handball courts in Baisley Pond Park, Police Officer Nicholas Demutiis Playground and Harvard Playground in Queens. | Queens | 2019-07-09 |  | Multisite in Queens | Construction
X040-116M | Poe Cottage Landscape and Accessible Path Reconstruction | This project will construct an accessible entrance to Poe Cottage and reconstruct surrounding landscape including planting, pavements and fencing. | Grand Concourse between East Kingsbridge Road and East 192nd Street | Bronx | 2019-07-10 |  | Poe Park | Construction
B210-116M | John J Carty Park Tennis Courts Reconstruction | This project will reconstruct the tennis courts in John J. Carty Park. | East side of Fort Hamilton Parkway between Marine Avenue and 101st Street | Brooklyn | 2019-07-10 | 2019-10-11 | John J Carty Park | Construction
Q302-116M | Evergreen Park Playground Reconstruction | This project will install new play equipment, pavement, fencing, drainage, site furniture, and lighting at the playground in Evergreen Park. | St. Felix Avenue between 60th Street and 60th Lane | Queens | 2019-07-15 |  | Evergreen Park | Completed
M402-116M | Chelsea Green Construction | This project will construct a new park, including play equipment, seating, lighting, plantings, and other site furnishings at Chelsea Green. | West 20th Street between 6th and 7th Avenues | Manhattan | 2019-07-15 |  | West 20th Street Park | Construction
Q021-117M | Cunningham Park Lower Playground Tot Lot Reconstruction | This project will reconstruct the Lower Playground (Redwood Playground) in Cunningham Park. | 193rd Street and Aberdeen Road | Queens | 2019-07-15 |  | Cunningham Park | Construction
MG-914MA | Manhattan General Site Work (MG-914MA) | This multi-site contract will reconstruct pavements, fencing, safety surfacing, play equipment, and construct handball courts and general site work in various locations in Manhattan. | Various locations, Manhattan | Manhattan | 2019-07-16 |  | Multisite in Manhattan | Completed
B095-116M | Ennis Playground Reconstruction | This project will reconstruct Ennis Playground. | 11th Street, 12th Street, 2nd Avenue, 3rd Avenue | Brooklyn | 2019-07-22 |  | Ennis Park | Construction
M257-117M | Clement Clarke Moore Park Reconstruction | This project will reconstruct Clement Clarke Moore Park. | Clement Clarke Moore Park is located on 10th Avenue between 21st and 22nd Streets | Manhattan | 2019-07-22 |  | Clement Clarke Moore Park | Construction
R117-115MA | Buono Beach and Alice Austen Reconstruction (Hurricane Sandy) | This project will reconstruct the landscape elements at Alice Austen House including picket fences and paths due to damage sustained during Hurricane Sandy. The project will also include the installation of security lighting. | Edgewater Street and Hylan Boulevard | Staten Island | 2019-07-22 |  | Alice Austen House & Park | Construction
Q104-114M | Queensbridge Park Field House Construction | This project will construct a field house in Queensbridge Park. | Located at Vernon Boulevard and the Ed Koch/Queensboro Bridge, Borough of Queens. | Queens | 2019-07-23 |  | Queensbridge Park | Construction
X010-115M | Crotona Park Ballfield 5 Reconstruction | This project will reconstruct ballfield 5 at Crotona Park with synthetic turf. | Crotona Park North and Crotona Avenue | Bronx | 2019-08-05 |  | Crotona Park | Construction
X004A-114M | Parque de los Ninos Softball Field and Running Track Construction | This project will reconstruct the softball field with a natural grass outfield and a running track with artificial turf multiuse infield at Parque de los Ninos. | Metcalf Avenue between Watson and Westchester Avenues | Bronx | 2019-08-05 |  | Bronx River Parkway | Construction
M230-116M | Poor Richard's Playground Entry Path Reconstruction | This project will reconstruct the 2nd Avenue entry path to Poor Richard's Playground with new benches, game tables, lighting, fencing, and landscaping. | East 108th Street at 2nd Avenue | Manhattan | 2019-08-05 |  | I.S. 117 & Ben Franklin Hs Plgd | Construction
MG-815M | Broadway Malls Reconstruction | This project will reconstruct landscapes, pavements, fences and benches at several malls along Broadway from West 102nd to 104th Streets and from West 137th to 139th Streets. | West 102nd to 104th Streets and West 137th to 139th Streets | Manhattan | 2019-08-12 |  | Multisite in Manhattan | Construction
M301-114M | St. Gregory's Playground Reconstruction | This project will reconstruct St. Gregory's Playground. | West 90th Street between Amsterdam and Columbus Avenues | Manhattan | 2019-08-19 |  | St. Gregory's Playground | Construction
Q009-114MA | MacNeil Park Esplanade Reconstruction | This project will reconstruct the esplanade in MacNeil Park. | Poppenheusen Avenue, East River, 115th Street, College Place, Queens | Queens | 2019-08-19 |  | Macneil Park | Construction
B093-117M | Weeksville Playground Reconstruction | This project will reconstruct Weeksville Playground with new play equipment, seating and planting beds. | Howard Avenue between Atlantic Avenue and Herkimer Street | Brooklyn | 2019-08-26 |  | Weeksville Playground | Construction
X168-117M | Nelson Playground Basketball Court and Bleachers Reconstruction | This project will reconstruct the basketball court and bleachers at Nelson Playground. | West 166th Street between Woodycrest Avenue and Nelson Avenue | Bronx | 2019-08-27 |  | Nelson Playground | Completed
B106-116M | Lafayette Playground Reconstruction | This project will reconstruct Lafayette Playground. | Benson Avenue, Bay 43rd Street, Stillwell Avenue | Brooklyn | 2019-08-28 | 2019-11-29 | Lafayette Playground | Construction
R016-214MA | New Dorp Center Interior Reconstruction (Hurricane Sandy) | This project will reconstruct the first floor of the New Dorp Center in Staten Island due to damage from Hurricane Sandy. | Cedar Grove Avenue in Great Kills Park, Staten Island | Staten Island | 2019-09-03 |  | Great Kills Park | Construction
B335-116M | Bildersee Playground Reconstruction Phase 1 | This project will construct a new synthetic turf field and reconstruct the basketball courts at Bildersee Playground. | Flatlands Avenue between East 81st Street and East 82nd Street | Brooklyn | 2019-09-03 |  | Bildersee Playground | Construction
QG-714M | Travers Park and Staunton Field Play Field Reconstruction | This project will reconstruct the asphalt play fields in Travers Park and Staunton Field, and construct a plaza within the 78th Street right-of-way. | 77th Street, Northern Boulevard, 79th Street, 34th Avenue, Queens | Queens | 2019-09-03 |  | Multisite in Queens | Construction
XG-32000-111M | Melrose Commons Park Construction | This project will construct a park in Melrose Commons Park. | Melrose Avenue between East 159th and East 160th Streets | Bronx | 2019-09-05 |  | Melrose Commons URA Site 32 | Construction
X010-114M | Crotona Park Nature Center Reconstruction | This project will reconstruct the Nature Center in Crotona Park. | Crotona Avenue and Crotona Park East in Crotona Park | Bronx | 2019-09-09 |  | Crotona Park | Construction
QG-1216M | Queens General Site Work (QG-1216M) | This project will reconstruct a stairway at Cunningham Park, the passive area of Brinkerhoff Mall, and fencing around the dog run in Forest Park, and construct a roller hockey rink at Broad Channel Park. | Various locations in Queens | Queens | 2019-09-14 |  | Multisite in Queens | Completed
B250-117M | Nostrand Playground Sport Courts Reconstruction | This project will reconstruct the basketball courts at Nostrand Playground. | Nostrand Avenue and Foster Avenue | Brooklyn | 2019-09-16 |  | Nostrand Playground | Construction
Q041-116M | Newtown Playground Reconstruction | This project will reconstruct paths and plantings on the upper lawn area of Newtown Playground. | 92nd Street and 56th Avenue | Queens | 2019-09-16 |  | Newtown Playground | Construction
B372-116M | Friends Field Playground Expansion | This project will reconstruct portions of the existing playground at Friends Field, including the removal of the existing safety surface, and the expansion of the existing playground area. | Avenue L and East 4th Street | Brooklyn | 2019-09-19 | 2019-12-31 | Friends Field Park | Construction
RG-416M | Carlton Park Landscape and Ida Court Playground Reconstruction | This project will reconstruct the play areas, paths, fencing, landscape and park amenities at Carlton Park and Ida Court Playground. | Carlton Park is located on Foster Road between Drumgoole Road and Carlton Avenue and Ida Court Playground is located on Ida Court Between Drumgoole Road East and North Railroad Street in the Borough of Staten Island. | Staten Island | 2019-09-21 |  | Multisite in Staten Island | Construction
M088-116M | Tompkins Square Playground Reconstruction | This project will reconstruct two playgrounds in Tompkins Square Park with new play equipment, safety surfacing, spray showers, seating, and fencing. | East 7th Street and Avenue B | Manhattan | 2019-09-23 |  | Tompkins Square Park | Construction
M238-117M | Bloomingdale Playground Comfort Station Reconstruction | This project will reconstruct the comfort station in Bloomingdale Park and bring it into compliance with ADA accessibility standards. | Amsterdam Ave, Between West 104th St. and West 105th St. | Manhattan | 2019-09-23 |  | Bloomingdale Playground | Construction
X171-116M | Spuyten Duyvil Playground Spray Shower Reconstruction | This project will reconstruct the spray shower at Spuyten Duyvil Playground. | Douglas Avenue between West 235th Street, and West 236th Street. | Bronx | 2019-09-24 |  | Spuyten Duyvil Playground | Construction
B339-216M | Newport Playground Reconstruction | This project will reconstruct Newport Playground. | Riverdale Avenue between Osborn Street and Thatford Avenue, adjacent to P.S. 41 | Brooklyn | 2019-09-26 | 2019-12-31 | Newport Playground | Construction
Q220-116M | Norelli-Hargreaves Playground Reconstruction | This project will reconstruct the seating area at Norelli-Hargreaves Playground. | Van Wyck Expressway, 142nd Street, 106th Avenue | Queens | 2019-09-30 |  | Norelli-Hargreaves Playground | Construction
M238-217M | Bloomingdale Playground Play Area Reconstruction | This project will reconstruct basketball courts, paths, benches, spray shower, planting, play equipment and adult fitness equipment at Bloomingdale Playground. | Amsterdam Avenue between West 104th Street and West 105th Street | Manhattan | 2019-10-06 |  | Bloomingdale Playground | Construction
Q102-117M | Juniper Valley Park Spray Shower Reconstruction | This project will reconstruct the spray shower in Juniper Valley Park. | Between 78th Street and 79th Street | Queens | 2019-10-07 |  | Juniper Valley Park | Construction
B128-115MA | Colonel David Marcus Playground Comfort Station Reconstruction | This project will reconstruct the comfort station in Colonel David Marcus Playground. | Avenue P between East 4th Street and East 5th Street | Brooklyn | 2019-10-08 |  | Colonel David Marcus Playground | Construction
X080-116M | Henry Hudson Park Basketball and Handball Courts Reconstruction | This project will reconstruct the basketball and handball courts at Henry Hudson Park. | Kappock Street between Independence Avenue and Palisade Avenue | Bronx | 2019-10-08 |  | Henry Hudson Park | Construction
X001-114M | Aqueduct Walk Plaza Reconstruction | This project will reconstruct the plaza, paths, and landscape in Aqueduct Walk. | Aqueduct Avenue between West 180th Street and West 181st Street | Bronx | 2019-10-08 |  | Aqueduct Walk | Construction
M099-117M | J. Hood Wright Park Adult Fitness Equipment Construction | This project will construct adult fitness equipment at J. Hood Wright Park. | Fort Washington Avenue between West 175th Street and West 176th Street | Manhattan | 2019-10-14 |  | J Hood Wright Park | Completed
B214-117M | Linden Park Synthetic Turf Field and Rubberized Track Reconstruction | This project will reconstruct the existing synthetic turf field and running track and construct new drinking fountains and sports field spray misters in Linden Park. | Linden Boulevard and Vermont Street | Brooklyn | 2019-10-14 |  | JHS 166, Linden Playground | Construction
Q299-117M | Overlook Park Seating Area Reconstruction | This project will reconstruct the seating area, paths, and plantings at Overlook Park. | Ditmars Boulevard, 98th Street, 99th Street, 22nd Drive | Queens | 2019-11-04 |  | Overlook Park | Construction
R167-113MA | Richmond Terrace Wetlands Streetscape Construction | This project will construct a seating area, overlook, paths, barrier rail, lighting and landscaping at the Richmond Terrace Wetlands. | Richmond Terrace between Van Name and Van Pelt Avenues, Staten Island | Staten Island | 2019-11-12 |  | Richmond Terrace Wetlands | Construction
B103-116M | Cypress Hills Playground Synthetic Turf Field Construction | This project will construct a new synthetic turf multi-purpose athletic field to replace an existing natural turf field at Cypress Hills Playground. The work will include a new perimeter recreation path, reconstructed dugouts, drinking fountains and misting stations. | Euclid Avenue, Blake Avenue, Dumont Avenue | Brooklyn | 2019-11-15 |  | Cypress Hills Park | Construction
M082-117M | Seward Park Reconstruction | This project will reconstruct a portion of Seward Park. | East Broadway, Canal Street, Essex Street | Manhattan | 2019-11-25 |  | William H. Seward Park | Construction
Q004-113MA | Astoria Park Diving Pool Reconstruction as a Plaza | This project will reconstruct the diving pool at the Astoria Park Bathhouse for use as an outdoor plaza. | 24-02 19th Street, between 23rd Street and 23rd Drive, Queens. | Queens | 2019-11-26 |  | Astoria Park | Construction
X148A2-117M | Plimpton Playground Reconstruction | This project will reconstruct the play equipment, swings, spray shower, seating, pavements, drainage systems, drinking fountain, fencing and entrance area at Plimpton Playground. | Edward L. Grant Highway and Plimpton Avenue | Bronx | 2019-11-27 |  | Plimpton Playground | Construction
X010-210MA3 | Crotona Park Bathhouse Entrance Reconstruction | This project will reconstruct the entrance towers, mezzanine roof and bridge at the entrance to the Crotona Park Bathhouse. | Fulton Avenue and East 173rd Street | Bronx | 2019-12-02 |  | Crotona Park | Construction
Q028-116M | Tribute Park Reconstruction (Hurricane Sandy) | This project will reconstruct Tribute Park due to damage from Hurricane Sandy. | Beach Channel Drive Between Beach 116th and Beach 117th Streets. | Queens | 2019-12-05 |  | Tribute Park | Construction
QG-1316M | Queens General Site Work (QG-1316M) | This project will construct new fitness equipment at Alley Pond Park and Alley Athletic Playground, reconstruct the seating area at One Room Schoolhouse Park, and construct a new meditation garden at Kissena Corridor Park. | Various locations in Queens | Queens | 2019-12-24 |  | Multisite in Queens | Construction
Q492-117M | Elmhurst Park Vietnam Veterans Memorial Construction | This project will construct a memorial to Vietnam War veterans from Queens in Elmhurst Park. | Grand Avenue between 57th Avenue and 79th Street | Queens | 2019-12-24 |  | Elmhurst Park | Construction
B008-418M | Betsy Head Park Multi-Purpose Play Area Reconstruction | This project will construct a new skate park, basketball courts, fitness area and multi-purpose space in the northern parcel of Betsy Head Park. | Blake Avenue between Thomas S. Boyland Street and Bristol Street | Brooklyn | 2019-12-30 |  | Betsy Head Memorial Playground | Construction