## Sheet
Parks' Contract # | FMS # | Property # | Short Description | Contract Summary | Contract Location | Borough | Construction SCD | Construction ACD | Final Inspection Date | Park Name | Contract Status
B028-116M | 846 P-210DBSF | B028 | Dyker Beach Park Synthetic Turf Soccer Field Reconstruction | This project will remove the existing deteriorated synthetic turf and replace with new synthetic turf at soccer field. The existing aggregate base and sub-surface drainage system shall remain and be reconstructed if necessary. The existing bleachers and drinking fountain will be reconstructed or replaced. | North of Shore Parkway in Dyker Beach Park, West of 14th Avenue, between Benson and Bath Avenues | Brooklyn | 2018-09-10 |  |  | Dyker Beach Park | Construction
B057-114M | 846 P-218D17S | B057 | Dr. John's Playground Paths, Water Supply & Drainage System Reconstruction | This project will reconstruct the paths, water supply and drainage systems at Dr. John's Playground. | Gerritsen Avenue and Avenue X, Brooklyn | Brooklyn | 2018-04-16 |  |  | MARINE PARK | Construction
B073-115M | 846 P-200PRRP | B073 | Prospect Park Internal Pathways Reconstruction | This project will reconstruct three existing pedestrian pathways with flooding, drainage and erosion issues. | Lake Path near Parkside Drive; Endale Arch near Flatbush and Prospect Park West; Litchfield Villa Parking Lot, near Prospect Park West and internal road West Drive. | Brooklyn | 2018-04-30 |  |  | Prospect Park | Construction
B073-216M | 846 P-200PPFB | B073 | Prospect Park Flatbush Avenue Perimeter Sidewalk Reconstruction | This project will reconstruct the damaged sidewalk and fencing along Flatbush Avenue. The new sidewalk will have exposed aggregate concrete, new ornamental fencing, a double row of street trees, benches, and light poles. | West side of Flatbush Avenue, from Grand Army Plaza to Prospect Park Zoo | Brooklyn | 2018-11-05 |  |  | Prospect Park | Construction
B073-316M | 846 P-200PATH | B073 | Prospect Park Dongan Oak Path and Drainage System Reconstruction | This project will reconstruct the pathways, drainage, and landscaping between the Dongan Oak marker and the Zucker Natural Exploration Area in Prospect Park. | Located within Prospect Park, north of Prospect Park Zoo, west of Flatbush Avenue, East of East Drive and south of Zucker Natural Exploration Area. | Brooklyn | 2018-05-14 |  | 2017-10-04 | Prospect Park | Completed
B080-116M | 846 P-213ALVY | B080 | Asser Levy Park Playground & Path Reconstruction | This project will reconstruct the playground and adjacent paths in Asser Levy Playground. | The playground and adjacent paths located on West 5th Street between Surf Avenue and Sea Breeze Avenue, in Asser Levy Park. | Brooklyn | 2018-10-15 |  |  | Asser Levy Park & Aquarium | Construction
B087-116M | 846 P-207SNST | B087 | Sunset Park Pavement, Fencing, and Bench Reconstruction | This project will reconstruct paths, benches and fencing in various locations within Sunset Park. | Various locations within Sunset Park, bounded by 5th and 7th Avenues, 41st and 44th Street | Brooklyn | 2018-09-24 |  |  | Sunset Park | Construction
B109-112M | 846 P-215BBPG | B109 | Bill Brown Memorial Park Comfort Station Reconstruction | This project will reconstruct the comfort station in Bill Brown Park. | Bedford Avenue and Avenue X to Avenue Y and 24th Street, Brooklyn | Brooklyn | 2016-08-15 | 2018-08-15 |  | Bill Brown Memorial Playground | Construction
B114-115M | 846 P-201MGRK | B114 | McGolrick Playground Reconstruction | This project will reconstruct the playground at McGolrick Park, including the play equipment, spray shower, pavement, fencing, benches, and plantings. | Nassau Avenue, Monitor Street, Russell Street and Driggs Avenue | Brooklyn | 2018-09-10 |  |  | Msgr. McGolrick Park | Construction
B118-115M | 846 P-206MARY | B118B | St. Mary's Playground Reconstruction | This project will construct new play equipment, benches, and pavements at St. Mary's Playground. | Huntington Street and Smith Street | Brooklyn | 2018-04-09 |  |  | St. Mary's Playground | Construction
B118-116M | 846 P-206SMRY | B118A | St. Mary's Playground Multi-Purpose Area Reconstruction | This project will reconstruct the existing multipurpose play area to include a skate park, basketball courts, multi-use synthetic turf field, adult fitness equipment and color seal coat walking track. | Smith Street between Nelson and Luquer Streets, Borough of Brooklyn | Brooklyn | 2018-10-01 |  |  | St. Mary's Playground | Construction
B150-115M | 846 P-214KOLB | B150 | Kolbert Playground Reconstruction | This project will reconstruct the handball courts and expand the play area to include new basketball courts, new synthetic turf field & walking track, new play equipment, and new adult fitness equipment. | Avenue L, East 17th and East 18th Streets | Brooklyn | 2018-04-23 |  |  | Kolbert Playground | Construction
B151-115M | 846 P-212DMPG | B151 | Dome Playground Sport Court Reconstruction | This project will reconstruct the basketball & handball courts located in Dome Playground. | Dahill Road & 38th Street, Brooklyn | Brooklyn | 2018-04-02 |  | 2018-03-05 | Dome Playground | Completed
B210-115M | 846 P-207JAPN | B210A | John Allen Payne Park Playground Reconstruction | This project will reconstruct the playground to include new play equipment, swings, and spray shower area. | 3rd Avenue between 64th and 65th Streets | Brooklyn | 2018-04-23 |  |  | John Allen Payne Park | Construction
B245-111M | 846 P-208K11E | B245 | St. John's Recreation Center Comfort Station Construction | This project will construct a comfort station adjacent to the St. John's Recreation Center. | Prospect Place between Troy and Schenectady Avenues, Brooklyn | Brooklyn | 2016-03-01 | 2018-07-02 |  | St. John's Recreation Center | Construction
B245-114M | 846 P-208HVAC | B245 | St. John's Recreation Center HVAC Reconstruction | This project will reconstruct the boilers and HVAC systems at St. John's Recreation Center. | Prospect Place between Troy and Schenectady Avenues, Brooklyn | Brooklyn | 2017-12-04 | 2018-08-06 |  | St. John's Park | Construction
B251-115M | 846 P-215MHAT | B251 | Manhattan Beach Sport Court Reconstruction | This project will reconstruct the basketball and handball courts located in Manhattan Beach Park. | Oriental Blvd and Falmouth Street, Brooklyn | Brooklyn | 2018-04-16 |  |  | Manhattan Beach Park | Construction
B255-116M | 846 P-207BTFY | B255G | Butterfly Gardens Pavement Reconstruction and Planted Area Expansion | This project will reconstruct pavements, expand existing planted areas and provide new site amenities including fencing, benches and trash receptacles. | 7th Avenue and 18th Street, South Slope, Brooklyn 11215 | Brooklyn | 2018-09-17 |  |  | Park | Construction
B263-114M | 846 P-203SUMN | B263 | Sumner Playground Ballfield and Athletic Court Reconstruction | This project will reconstruct Sumner Playground. | Throop Avenue between Park and Myrtle Avenues, Brooklyn | Brooklyn | 2018-09-24 |  |  | Sumner Playground | Construction
B269-116M | 846 P-2CPIJOP | B269 | Jesse Owens Playground Reconstruction | This project will reconstruct the play equipment, spray shower, synthetic turf field, painted track, lighting, fencing, pavement, plantings and furnishings at Jesse Owens Playground. | 125 Stuyvesant Ave, Brooklyn, NY 11221 | Brooklyn | 2018-09-21 |  |  | Jesse Owens Playground | Construction
B298-116MA | 846 P-2CPISTK | B298 | Stockton Playground Reconstruction | This project will construct new play equipment, including a spray shower, synthetic turf field and painted track; lighting; fencing; pavement; planting and site furnishings at Stockton Playground. | 662 Park Avenue, Brooklyn, NY 11206 | Brooklyn | 2018-03-30 |  |  | Stockton Playground | Construction
B311-116M | 846 P-2CPITEN | B311 | Ten Eyck Playground Reconstruction | This project will construct new play equipment, including a spray shower, a synthetic turf field, a painted track, and a basketball court; lighting; fencing; pavement; planting and site furnishings at Ten Eyck Playground. | 242 Scholes Street, Brooklyn, NY 11206 | Brooklyn | 2018-03-30 |  |  | Ten Eyck Playground | Construction
B316-114M | 846 P-214DIGI | B316 | Di Gilio Playground Reconstruction | This project will reconstruct Di Gilio Playground. | McDonald Avenue and Avenue F, Brooklyn | Brooklyn | 2018-04-23 |  |  | Di Gilio Playground | Construction
B353-116M | 846 P-2CPIBGB | B353 | Bergen Beach Playground Reconstruction | This project will reconstruct Bergen Beach Playground. | 71st Street between Avenue N and Avenue T, adjacent to P.S.312, in Brooklyn | Brooklyn | 2018-09-24 |  |  | Bergen Beach Playground | Construction
B376-111MA | 846 P-217WYKF | B376 | Wyckoff House Roof Reconstruction | This project will reconstruct the roof at the Wyckoff House in M. Fidler/Wyckoff House Park. | Ditmas Avenue and Clarendon Road, Brooklyn. | Brooklyn | 2018-07-04 |  |  | M Fidler-Wyckoff House Park | Construction
B381-115M | 846 P-2CPITBP | B381 | Thomas Boyland Park Reconstruction | This project will reconstruct the play areas, adult fitness equipment, seating area, basketball courts, and baseball field at Thomas Boyland Park. | THOMAS BOYLAND PARK | Brooklyn | 2018-01-09 |  | 2017-08-11 | Thomas Boyland Park | Completed
B395-115MA1 | 846 P-204GRCK | B395 | Green Central Knoll Comfort Station Construction | This project will construct a new comfort station and adjacent landscape work in Green Central Knoll. | Evergreen Avenue and Knoll Street, Brooklyn | Brooklyn | 2018-06-18 |  |  | Green Central Knoll | Construction
B406-114M | 846 P-217PDGT | B406 | Paerdegat Athletic Center Air Conditioning Reconstruction | This project will reconstruct the air conditioning equipment. | PAERDEGAT AVENUE NORTH, BETWEEN PAERDEGAT 13TH STREET AND SEAVIEW AVENUE, Borough of BROOKLYN | Brooklyn | 2018-03-19 | 2018-09-22 |  | Paerdegat Basin Park | Construction
B536-113M | 846 SANDY2-10 | B536 | North 5th Street Bulkhead Reconstruction (Hurricane Sandy) | This project will reconstruct the North 5th Street bulkhead in Brooklyn, which was damaged by Hurricane Sandy. | Kent Avenue between North 4th and North 5th Streets, Brooklyn | Brooklyn | 2018-10-01 |  |  | North 5th Street Pier | Construction
BG-1408MA | 846 P-2PNYTP2 | NA | FY09 Street Tree Procurement (BG-1408MA) (PURCHASE ONLY) |  |  | Brooklyn | 2017-08-14 | 2018-07-27 |  | Multisite in Brooklyn | Construction
BG-213MA | 846 P-2BWCC07 | NA | McKinley Park and Seth Low Playground Synthetic Turf Ballfield Reconstruction | This multisite contract will construct new synthetic turf ballfields and McKinley Park and Seth Low Playground. | Bay Ridge Parkway between 7th Avenue and Fort Hamilton Parkway; Avenue P, Bay Parkway, West 12th Street, Brooklyn | Brooklyn | 2018-03-05 |  | 2017-09-14 | Multisite in Brooklyn | Completed
BG-216M | 846 P-2PNYT28 | NA | Brooklyn Street Tree Planting FY17 - Community Boards 5,14,18 | This project will plant new trees in community boards 5,14,18 in Brooklyn. | Various locations, in Brooklyn community boards 5,14,18. | Brooklyn | 2018-10-01 |  |  | Multisite in Brooklyn | Construction
BG-416M | 846 P-2PNYT29 | NA | Brooklyn Street Tree Planting FY17 - Community Boards 8,9,17 | This project will plant new trees in community boards 8,9,17 in Brooklyn. | Various locations, in Brooklyn community boards 8,9,17. | Brooklyn | 2018-10-11 |  |  | Multisite in Brooklyn | Construction
BG-516M | 846 P-2TRE17C | NA | Brooklyn Street Tree Planting FY17 - Community Boards 11,13,15 | This project will plant new trees in community boards 11,13,15 in Brooklyn. | Various locations, in Brooklyn community boards 11,13,15. | Brooklyn | 2018-09-24 |  |  | Multisite in Brooklyn | Construction
BG-815MA | 846 P-2CPIBN2 | NA | Jesse Owens, Stockton and Stroud Playgrounds Comfort Station Reconstruction | This project will reconstruct the comfort stations Jesse Owens Playground, Stockton Playground, and Stroud Playground. | Various locations in Brooklyn | Brooklyn | 2018-12-19 |  |  | Multisite in Brooklyn | Construction
BG-915M | 846 P-2BELTPD | B018 | Canarsie West Trail Connector Construction | This project will construct a multi-use greenway path connecting the on-street path along Paerdegat Avenue North to the Shore Parkway Greenway along the southwestern edge of Canarsie Park. | Paerdegat Avenue North & Seaview Avenue to Shore Parkway | Brooklyn | 2018-05-21 |  |  | Canarsie Park | Construction
CNYG-1115M | 846 P-6ROOF15 | NA | Citywide Roofing Reconstruction (CNYG-1115M) | This project will reconstruct roofs on Parks facilities, citywide. | Various locations, citywide |  | 2018-07-29 |  |  | Multisite Citywide | Construction
CNYG-1212M | 846 P-6ASBE13 | NA | Citywide Facility Indoor Air Quality Testing (CNYG-1212M) | This multisite contract will perform indoor air quality tests at various facilities citywide. | Various locations, citywide |  | 2017-05-18 | 2018-05-18 |  | Multisite Citywide | Construction
CNYG-1212MR | 846 EXPENSE42_PC-002226 | NA | Citywide Air Quality Testing, Bulk Sampling and Soil Testing (CNYG-1212MR) | This project will perform indoor air quality tests at various facilities, citywide. This is a renewal of CNYG-1212M, the new name should be CNYG-1212MR | Various locations, citywide |  | 2018-05-18 |  |  | Multisite Citywide | Construction
CNYG-1409M PLANYC | 846 P-6PNYR03 | NA | Bronx, Brooklyn and Queens Area A Street Tree Procurement For Region 1 | PROCUREMENT OF TREES FROM REGION 1 FOR THE BOROUGHS OF QUEENS AREA A, THE BRONX & BROOKLYN |  |  | 2018-09-22 | 2018-09-22 |  | Multisite Citywide | Construction
CNYG-1515M | 846 P-6POGC15 | NA | Citywide Pool Structural Work (CNYG-1515M) | This project will reconstruct structural systems at pools, citywide. | Various locations, citywide |  | 2018-10-11 |  |  | Multisite Citywide | Construction
CNYG-1708MA PLANYC | 846 P-6PNYT09 | NA | Manhattan and Staten Island Street Tree Procurement for Region 3 | PROCUREMENT OF STREET TREES FROM REGION 3 FOR THE BOROUGHS OF MANHATTAN & STATEN ISLAND |  |  | 2017-08-29 | 2018-08-29 |  | Multisite Citywide | Construction
CNYG-1815M | 846 P-6PBUT15 | NA | Citywide Plumbing Utility Work (CNYG-1815M) | This project will reconstruct site utility plumbing systems, citywide. | Various locations, citywide. |  | 2018-08-07 |  |  | Multisite Citywide | Construction
CNYG-1909M PLANYC | 846 P-6PNYR08 | NA | Manhattan, Queens Area B and Staten Island Street Tree Procurement for Region 3 | PROCUREMENT OF TREES FROM REGION 3 FOR THE BOROUGHS OF MANHATTAN, S.I. & QUEENS AREA B. |  |  | 2018-10-18 | 2018-10-18 |  | Multisite Citywide | Construction
CNYG-1910MA1 | 846 P-6REC11B | NA | Brooklyn, Queens and Staten Island Recreation and Nature Center HVAC Repair (CNYG-1910MA1) | This multisite contract will reconstruct HVAC systems at recreation centers and nature centers in Queens, Brooklyn and Staten Island. | Various locations, Queens, Brooklyn and Staten Island |  | 2018-10-31 |  |  | Multisite Citywide | Construction
CNYG-215M | 846 P-6PNYR27 | NA | Brooklyn and Staten Island Reforestation FY15 | This project will remove invasive species and plant new trees in Brooklyn and Staten Island. | Various parks in Brooklyn and Staten Island |  | 2017-10-16 | 2018-06-30 |  | Multisite Citywide | Construction
CNYG-2709MA | 846 P-6BLDG9E | M105 | Sara D. Roosevelt Park Building C Fire Alarm Installation |  |  | Citywide | 2013-07-15 | 2018-06-29 |  | SARA D. ROOSEVELT PARK | Construction
CNYG-3215M | 846 P-6CPIBN3 | NA | Luther Gulick, Lyons Square, Saw Mill, Melrose Commons and Ten Eyck Playgrounds Comfort Station Construction | This project will construct comfort stations at various locations in Brooklyn, the Bronx, and Manhattan. | Ten Eyck Playground, Brooklyn; Lyons Square Playground, Bronx; Melrose Commons Playground, Bronx; Saw Mill Playground, Bronx; Luther Gulick Playground, Manhattan |  | 2018-08-30 |  |  | Multisite Citywide | Construction
CNYG-3315M | 846 P-6CPIBN4 | NA | Hunts Point, Playground 52, Carmansville, MLK, and Sol Lain Playgrounds Comfort Station Reconstruction | This project will reconstruct comfort stations in various locations in the Bronx and Manhattan. | Hunts Point Playground, Bronx; Playground 52, Bronx; Carmansville Playground, Manhattan; Martin Luther King Playground, Manhattan; Sol Lain Playground, Manhattan |  | 2018-01-05 | 2018-04-02 |  | Multisite Citywide | Construction
CNYG-3516MA | 846 SANDY6-18 | NA | Bronx, Manhattan and Queens Sandy-Related and Risk Management Tree Removal | This project will remove Hurricane Sandy-damaged trees in the Bronx, Manhattan and Queens. | Various locations, the Bronx, Manhattan and Queens. |  | 2018-09-10 | 2018-09-10 |  | Multisite Citywide | Construction
CNYG-3616MA | 846 SANDY6-17 | NA | Brooklyn and Staten Island Sandy-Related and Risk Management Tree Removal | This project will remove trees damaged from Hurricane Sandy and for Risk Management in the Boroughs of Brooklyn and Staten Island. | Various locations, Brooklyn and Staten Island |  | 2018-09-10 | 2018-09-10 |  | Multisite Citywide | Construction
CNYG-409MA | 846 P-6BLDG9C | NA | Citywide Comfort Station Plumbing Systems Reconstruction (CNYG-409MA) | This project will reconstruct the plumbing systems at comfort stations citywide. | Various locations citywide | Citywide | 2014-07-28 | 2018-06-29 |  | Multisite Citywide | Construction
CNYG-415M | 846 P-6PDRFSB | NA | Brooklyn and Staten Island Roofing Systems Reconstruction (CNYG-415M) | This project will reconstruct the roofing systems at various facilities in Brooklyn and Staten Island. |  |  | 2018-03-02 |  | 2017-07-10 | Multisite Citywide | Completed
CNYG-514M | 846 P-6RETW14 | NA | Citywide Retaining Walls and Seawalls Reconstruction (CNYG-514M) | This project will reconstruct and stabilize retaining walls and seawalls in parks citywide. | Various locations, citywide |  | 2017-11-02 | 2018-08-20 |  | Multisite Citywide | Construction
CNYG-614M | 846 P-6PLEL14 | NA | Citywide Pool Electrical Systems Reconstruction (CNYG-614M) | This project will reconstruct deteriorated electrical systems at various pools citywide. | Various locations, citywide |  | 2018-10-04 |  |  | Multisite Citywide | Construction
CNYG-713MA | 846 P-6HAZM13 | NA | Citywide Asbestos and Lead Removal and Disposal (CNYG-713MA) | This project will remove asbestos and lead at various facilities citywide. | Citywide |  | 2018-07-14 |  |  | Multisite Citywide | Construction
CNYG-714M | 846 P-6PLPB14 | NA | Citywide Pool Plumbing Systems Reconstruction (CNYG-714M) | This project will reconstruct deteriorated plumbing systems at pools citywide. | Various locations, citywide |  | 2018-04-05 |  | 2018-04-04 | Multisite Citywide | Completed
M029-111MA | 846 P-312FTSR | M029 | Fort Tryon Park Fieldhouse Staircase Reconstruction | This project will reconstruct the staircase and perform site work at the Fort Tryon Park fieldhouse. | Broadway between Arden Street and Dongan Place, Manhattan | Manhattan | 2018-03-05 |  | 2018-03-05 | Fort Tryon Park | Completed
M042-115M | 846 P-312IHPB | M042 | Inwood Hill Park Nature Center Sewer Connection Construction | This project will install approximately 600 LF of sewer line connecting the Nature Center and the DEP Sewer main at 218th street. | Inwood Hill Park between Henry Hudson Parkway and Indian Road intersection with 218th Street | Manhattan | 2018-07-09 |  |  | Inwood Hill Park | Construction
M047-116M | 846 P-3EHSKAT | M047 | Thomas Jefferson Park East Harlem Skate Park Construction | This project will construct a skate park in the northeast corner of the existing playground in Thomas Jefferson Park. | Thomas Jefferson Park located at the northeast corner of 114th Street and the FDR Drive, Borough of Manhattan | Manhattan | 2018-03-05 |  | 2017-09-27 | Thomas Jefferson Park | Completed
M058-115M | 846 P-311MGFI | M058 | Marcus Garvey Park Fire Watchtower Restoration | This project will reconstruct the fire watchtower and surrounding plaza in Marcus Garvey Park. | Marcus Garvey Park Madison Avenue at E122nd Street | Manhattan | 2018-07-09 |  |  | Marcus Garvey Memorial Park | Construction
M073-114M | 846 P-312MJOR | M073 | Morris-Jumel Mansion Octagon Room Air Conditioning Installation | This project will install an air conditioning system, perform electrical upgrades and restore finishes in the Octagon Room at the Morris Jumel Mansion in Roger Morris Park. | West 160th Street and Edgecombe Avenue, Manhattan | Manhattan | 2018-03-04 |  |  | Roger Morris Park | Construction
M108-113M | 846 P-3SUTTON | M108R | Sutton Place Park Reconstruction (M108-113M) | This project will reconstruct a portion of Sutton Place Park. | FDR Drive between 56th and 57th Streets, Manhattan | Manhattan | 2018-06-18 |  |  | Sutton Place Park | Construction
M111-115M | 846 P-3CPIJWJ | M111 | James Weldon Johnson Playground Reconstruction | This project will reconstruct the playground, active recreation and joint operated playground with the adjacent school. | South of 115th Street, Between Third Avenue and Lexington Avenue | Manhattan | 2018-02-19 |  | 2018-02-16 | James Weldon Johnson Playground | Completed
M144-214MA | 846 P-303ERSF | M144 | East River Park East 6th Street Synthetic Turf Soccer Field & Running Track Reconstruction | This project will reconstruct the synthetic turf soccer field and resurface the running track at East 6th Street in East River Park. | East 6th Street and East River Park, Manhattan | Manhattan | 2018-09-10 |  |  | East River Park | Construction
M154-114MA | 846 P-304MPPR | M154 | Mathews-Palmer Playground Reconstruction | This project will reconstruct Mathews-Palmer Playground. | West 45th Street between 9th and 10th Avenues, Manhattan | Manhattan | 2018-04-23 |  |  | Mathews - Palmer Playground | Construction
M211-110MA2 | 846 P-309STNC | M211B | St. Nicholas Playground North Comfort Station Reconstruction | This project will reconstruct the comfort station at St. Nicholas North Playground. | Adam Clayton Powell Jr. Boulevard and West 130th Street, Manhattan | Manhattan | 2017-10-09 | 2018-05-15 |  | St. Nicholas Playground North | Construction
M218-114M | 846 P-302DPCA | M218 | DeSalvio Playground Adult Use and Children's Play Area Reconstruction | This project will reconstruct DeSalvio Playground. | Mulberry and Spring Streets, Manhattan | Manhattan | 2018-07-16 |  |  | DeSalvio Playground | Construction
M353-112M | 846 P-307RPKS | M353 | Riverside Park South Playground, Bikeway, and Site Work Construction | This project will construct plazas, a playground, a bikeway and miscellaneous site work between West 62nd and West 69th Streets in Riverside Park South. | West 62nd to West 69th Streets in Riverside Park South, Manhattan | Manhattan | 2018-08-28 |  |  | Riverside Park South | Construction
MG-216M | 846 P-3CPIBN9 | NA | Playground 103 and St Nicholas North Playground Reconstruction | This project will reconstruct Playground 103 and St. Nicholas Playground North. | First site: Playground 103, Located along the FDR Drive Between East 102nd Street and East 105th Street, Borough of Manhattan. Second site: St. Nicholas Playground North, Located on Adam Clayton Powell Jr. Boulevard between West 129th and West 131st Streets, Borough of Manhattan | Manhattan | 2018-05-29 |  |  | Multisite in Manhattan | Construction
MG-25000-116M | 846 P-3SOHO | MZ02 | Spring Street Park Reconstruction | This project will reconstruct Spring Street Park (Soho Square). | 6th Avenue betwen Spring Street and Broome Street. | Manhattan | 2018-09-01 |  |  | Spring Street Park | Construction
MG-315MA1 | 846 P-3PLG14C | NA | Manhattan General Site Work (MG-315MA1) | This project will reconstruct pavements, basketball courts, fencing and general site work at various locations in Manhattan. | Various Locations, Manhattan | Manhattan | 2018-10-15 |  |  | Multisite in Manhattan | Construction
MG-416M | 846 P-3TRE17A | NA | Manhattan Street Tree Planting FY17 | This project will plant new trees in community boards 1-12 in Manhattan. | Various locations, Manhattan. | Manhattan | 2018-10-24 | 2018-10-24 |  | Multisite in Manhattan | Construction
MG-512M | 846 P-3FFAGAN | NA | Father Fagan Park Sitting Area Reconstruction and Charlton Plaza Water Service Installation | This multisite contract will reconstruct the sitting area in Father Fagan Park and install water service at Charlton Plaza. | Avenue of the Americas between Prince and Vandam Streets; Avenue of the Americas and Charlton Street, Manhattan | Manhattan | 2018-06-04 |  |  | Multisite in Manhattan | Construction
MG-614M | 846 P-6RFMN14 | NA | Manhattan Roofing Systems Reconstruction (MG-614M) | This project will reconstruct roofing systems in Manhattan. | Various locations, Manhattan | Manhattan | 2018-09-05 |  | 2017-09-20 | Multisite in Manhattan | Completed
MG-615M | 846 P-3PLG15C | NA | Manhattan Basketball Court Reconstruction | This project will reconstruct basketball and tennis courts at various locations in Manhattan. | P.S. 125 BASKETBALL COURTS - West 123rd St. & Morningside Ave. THOMAS JEFFERSON BASKETBALL COURTS - West 111th St. & Pleasant Ave. HAMILTON FISH BASKETBALL COURTS - Stanton St. & Pitt SEWARD PARK - Essex St. & Straus Sq. EAST RIVER TENNIS COURTS - FDR & E. Houston Str. | Manhattan | 2018-03-27 |  | 2018-03-26 | Multisite in Manhattan | Completed
Q008-115M | 846 P-413BPTC | Q008 | Brookville Park Picnic Area Reconstruction and Tennis Courts Construction | This project will reconstruct the picnic area and construct a tennis court and lighting at Brookville Park. | Brookville Boulevard, 232nd Street, 144th Avenue and 145th Avenue. | Queens | 2018-07-23 |  |  | Brookville Park | Construction
Q014-115M | 846 P-4CPIAST | Q014 | Astoria Heights-JHS10 Playground Reconstruction | This project will reconstruct Astoria Heights Playground, Borough of Queens. | 30th Road between 45th and 46th Streets Borough of Queens | Queens | 2018-05-08 |  |  | Astoria Heights Playground | Construction
Q021-115M | 846 P-408CPPA | Q021 | Cunningham Park Picnic Area Reconstruction and Performance Area Construction | This project will reconstruct the picnic area and the adjacent pathways, and construct a performance area in Cunningham Park. | Grand Central Parkway between 193rd Street, Francis Lewis Boulevard, Hollis Hills Terrace and 210th Street. | Queens | 2018-09-11 |  |  | Cunningham Park | Construction
Q099-115M | 846 P-415ENTR | Q099 | FMCP Roosevelt Avenue Entrance Reconstruction | This project will reconstruct the entrance east of Grand Central Parkway between Roosevelt Avenue and the LIRR in Queens. | In Flushing Meadows Corona Park, east of Grand Central Parkway between Roosevelt Avenue and the LIRR | Queens | 2018-08-25 |  |  | Flushing Meadows Corona Park | Construction
Q099-417M | 846 FMCPROOF | Q099 | Flushing Meadows Corona Park Pool Emergency Roof Reconstruction | This project will reconstruct the roof at the Flushing Meadows Corona Park Pool. | 131-04 Meridian Road, Flushing, NY 11368 | Queens | 2018-02-01 |  | 2017-10-13 | Flushing Meadows Corona Park | Completed
Q099-808MA1 | 846 P-4OLMST4 | Q099 | Olmsted Center Reconstruction | This project will reconstruct the existing Olmsted Center in Flushing Meadows-Corona Park. | 117-02 Roosevelt Avenue, Queens | Queens | 2016-10-31 | 2018-11-30 |  | Flushing Meadows Park | Construction
Q106-113M | 846 P-412DOP2 | Q106 | O'Connell Playground Recreation Building Reconstruction | This project will reconstruct the recreation building in Daniel M. O'Connell Playground. | Murdoch and 113th Avenues, 196th and 197th Streets, Queens | Queens | 2017-06-20 | 2018-06-29 |  | Daniel M. O'Connell Playground | Construction
Q135-115MA | 846 SANDY4-19 | Q135 | Bayside Marina Electrical Reconstruction (Hurricane Sandy) | This contract will replace electrical equipment, conduits and cable damaged by Hurricane Sandy at Bayside Marina. | Bayside Marina, 28-05 Cross Island Parkway, Bayside | Queens | 2018-09-17 |  |  | Cross Island Parkway | Construction
Q135-214M | 846 P-401JOEM | Q135 | Joe Michael's Mile Reconstruction | This project will reconstruct the southern portion of Joe Michael's Mile. | Located between 28th Avenue Southeast to Northern Boulevard, Little Neck Bay and The Cross Island Parkway | Queens | 2018-09-04 |  |  | Cross Island Parkway | Construction
Q164-115MA | 846 P-414RBLT | Q164 | Rockaway Beach Lifeguard Trailer Furnishing and Installation | This project will install a prefabricated lifeguard trailer and comfort station. | Beach 149th Street and Rockaway Beach Boulevard | Queens | 2018-02-28 |  | 2017-06-30 | Rockaway Beach & Boardwalk | Completed
Q205A-115M | 846 P-4BIGBSH | Q205A | Big Bush Park Playground Reconstruction | This project will reconstruct the playground, spray shower, handball courts, sitting area, fencing and pavements in Big Bush Park. | Big Bush Park located at Laurel Hill Boulevard between 61st and 64th street, Borough of Queens | Queens | 2018-04-30 |  |  | Bush Park | Construction
Q300-116M | 846 P-4CARSON | Q300 | Silent Spring Playground Reconstruction | This project will reconstruct Silent Spring Playground. | Colden Street between Juniper and Geranium Avenues in Kissena Corridor Park, Borough of Queens | Queens | 2018-12-10 |  |  | KISSENA CORRIDOR PARK | Construction
Q353-115M | 846 P-4CPIGRS | Q353 | Grassmere Playground Reconstruction | This project will reconstruct the play equipment, swings, landscaping, and sitting areas in Grassmere Playground. | This project is located East of Hanson Court, between Grassmere Terrace and Briar Place, in the Borough of Queens. | Queens | 2018-05-15 |  | 2017-11-20 | Grassmere Playground | Completed
Q366-116M | 846 P-403MOS2 | Q366 | Louis C. Moser Park Playground Reconstruction | This project will reconstruct the playground at Louis C. Moser Park. | 77th Street and 25th Avenue | Queens | 2018-09-10 |  |  | Louis C. Moser Park | Construction
Q391-116M | 846 P-408AUS2 | Q391 | Joseph Austin Playground Synthetic Turf Field Reconstruction | This project will reconstruct the synthetic turf ballfield and drainage system at Joe Austin Playground. | Located at the intersection of The Grand Central Parkway and 164th Place and 168th Street, Borough of Queens | Queens | 2018-08-13 |  |  | Joseph Austin Playground | Construction
Q392-115M | 846 P-4IDLEPK | Q392 | Idlewild Park Forest Restoration and Tree Planting | This project will prepare planting sites for invasive species removals including the planting of new and replacement trees at Idlewild Park. | Idlewild Park | Queens | 2018-05-15 | 2018-12-31 |  | Idlewild Park | Construction
Q394-115M | 846 P-4CPIRCP | Q394 | Conch Playground Reconstruction | This project will reconstruct Conch (PS.105) Playground. | Located at Beach Channel Drive between Beach 49th Street and Beach 51st Street | Queens | 2018-05-09 |  | 2018-01-18 | Conch Playground | Completed
Q446-216M | 846 P-414SRHV | Q446 | Sorrentino Recreation Center Boiler Reconstruction and HVAC Construction | This project will reconstruct boilers and provide a new heating, ventilation, and air conditioning system for the gymnasium. | 18-48 Cornaga Ave Between Beach 19th Street and Mott Ave | Queens | 2018-07-09 |  |  | Sorrentino Recreation Center | Construction
Q448-116M | 846 P-412RWTT | Q448 | Roy Wilkins Turf, Track and Field Reconstruction | This project will reconstruct a running track and synthetic turf field and related site work. | Merrick Boulevard between 116th Avenue and 118th Road Borough of Queens | Queens | 2018-11-12 |  |  | Roy Wilkins Recreation Center | Construction
Q474-115M | 846 P-4CPICMA | Q474 | Louis Simeone Park Reconstruction | This project will construct new pavements, drainage, benches, game tables, fencing, fitness equipment and planting at Louis Simeone Park. | Bounded by 101 Street, Lewis, Strong and Radcliff Avenues in the Borough of Queens. | Queens | 2018-01-31 |  | 2018-01-29 | Simeone Park | Completed
QG-1015M | 846 P-4CPIBN5 | NA | Astoria Heights and Bowne Playground Comfort Station Reconstruction | This project will reconstruct the comfort stations at Astoria Heights Playground and Bowne Playground. | Astoria Heights Playground and Bowne Playground | Queens | 2018-06-06 |  |  | Multisite in Queens | Construction
QG-1313M | 846 P-4PLG13F | NA | Queens General Site Work (QG-1313M) | This multisite contract will reconstruct play equipment, pavements, fencing, water supply, drainage, site features, plantings and general site work in Queens. | Various locations, Queens | Queens | 2017-05-02 | 2018-03-31 | 2018-02-28 | Multisite in Queens | Completed
QG-1413MA | 846 P-6BLDG13 | NA | Queens General Comfort Station and Facility Reconstruction (QG-1413MA) | This project will reconstruct comfort stations and facilities at various parks and recreation locations in Queens. | Various locations, Queens | Queens | 2017-09-12 | 2018-04-30 |  | Multisite in Queens | Construction
QG-1808MA PLANYC | 846 P-4PNYT08 | NA | Queens Street Tree Procurement for Region 2 | PROCUREMENT OF STREET TREES FROM REGION 2 FOR COMMUNITY BOARDS 1-14, BOROUGH OF QUEENS |  | Queens | 2017-08-08 | 2018-08-08 |  | Multisite in Queens | Construction
QG-1908MA PLANYC | 846 P-4PNYT09 | NA | Queens Street Tree Procurement for Region 3 | PROCUREMENT OF STREET TREES FROM REGION 3 FOR COMMUNITY BOARDS 1-14, BOROUGH OF QUEENS |  | Queens | 2017-08-29 | 2018-08-29 |  | Multisite in Queens | Construction
QG-1913M | 846 P-4PLG13M | NA | Queens General Site Work (QG-1913M) | This multisite contract will reconstruct play equipment, pavements, fencing, water supply, drainage, site features, plantings and general site work in Queens. | Various locations, Queens | Queens | 2018-03-08 |  |  | Multisite in Queens | Construction
QG-715M | 846 P-4PLAY15 | NA | Queens General Site Work (QG-715M) | This project will reconstruct pavements, fencing, safety surface, play equipment, drainage and miscellaneous site work at various locations in the borough of Queens | Various locations in the borough of Queens, this is the dollar contract, the parent contract. | Queens | 2018-04-03 | 2018-09-28 |  | Multisite in Queens | Construction
QG-716M | 846 P-4PNYT27 | NA | Queens Street Tree Planting FY17 - Community Boards 1-5 | This project will plant new trees in community boards 1-5 in Queens. | Various locations, in Queens community boards 1-5 | Queens | 2018-10-11 | 2018-10-11 |  | Multisite in Queens | Construction
QG-815M | 846 P-4PLG15C | NA | Austin, Giovanelli, and Utopia Playgrounds Reconstruction | This project will reconstruct various playgrounds in Queens. The work will include pavements, play equipment, fencing, safety surface, drainage systems, tree work and benches. | 1. Ehrenreich - Austin Playground (Q304) Located along southwest side of Austin Street between 76th Avenue and 76th Drive, 2. Utopia Playground (Q294) bounded by Utopia Parkway, 73rd Avenue and Jewel Avenue, and 3. Giovannelli Playground (Q015) located at northwest corner of Park Lane South and Freedom Drive. | Queens | 2018-02-12 |  | 2017-12-20 | Multisite in Queens | Completed
QG-816M | 846 P-4TRE17A | NA | Queens Street Tree Planting FY17 - Community Boards 6,9,10 | This project will plant new trees in community boards 6,9,10 in Queens. | Various locations, in Queens community boards 6,9,10. | Queens | 2018-10-01 | 2018-10-01 |  | Multisite in Queens | Construction
QG-915M | 846 P-4PLG15H | NA | Queens General Site Work (QG-915M) | This project will reconstruct pavements, fencing and drainage systems at various parks in Queens. | Various locations in Queens | Queens | 2018-06-26 |  | 2016-11-22 | Multisite in Queens | Completed
QG-916M | 846 P-4PNYT28 | NA | Queens Street Tree Planting FY17 - Community Boards 7,8,11 | This project will plant new trees in community boards 7,8,11 in Queens. | Various locations, in Queens community boards 7,8,11. | Queens | 2018-10-25 |  |  | Multisite in Queens | Construction
R031-115M | 846 SANDY5-26 | R031 | Wolfe's Pond Park Playground Reconstruction (Hurricane Sandy) | This project will reconstruct the Sandy-damaged playground and adjacent pathways, including installation of new full depth asphalt pavement for existing paths, the removal and reinstallation of all existing safety surfacing surrounding the play equipment as well as repairs to existing chain link fencing, benches and curbs. | The playground is located along the shoreline of Wolfe''s Pond Park at Cornelia Avenue and the Raritan Bay. | Staten Island | 2018-05-14 |  |  | Wolfes Pond Park | Construction
R033-115M | 846 P-5CPILEV | R033 | Levy Playground Reconstruction | This project will reconstruct the existing playground in Levy Playground with a new basketball court, play equipment, safety surfacing, interactive water features and landscaping. | Levy Playground is located at the intersection of Jewett and Castleton Avenues in Staten Island. | Staten Island | 2018-05-21 |  |  | Levy Playground | Construction
R034-115M | 846 P-5CPIMDP | R034 | Austin J. McDonald Park Playground and Multi-Use Area Reconstruction | This project will reconstruct the playground and multi-use area at McDonald Playground. | Forest Avenue, Myrtle Avenue, Broadway, North Burgher Avenue. | Staten Island | 2018-04-02 | 2018-04-30 |  | McDonald Playground | Construction
R035-115M | 846 P-5CPIDMT | R035 | DeMatti Playground Reconstruction | This project will reconstruct the multi use area and upgrade elements to increase universal accessibility. | West of Tompkins Avenue, between Chestnut Street and Shaughnessy Lane, Borough of Staten Island. | Staten Island | 2018-03-06 |  | 2018-02-27 | De Matti Playground | Completed
R068-115MA | 846 P-5CPIGVP | R068 | Grandview Playground Reconstruction | This project will reconstruct the playground, courts, and multi-use fields in Grandview Playground. | Grandview Avenue & Continental Place. | Staten Island | 2018-04-24 |  |  | Grandview Playground | Construction
R145-115M | 846 SANDY5-24 | R145 | Nelson Avenue Waterfront Park Reconstruction (Hurricane Sandy) | This project will repair the Hurricane Sandy-damaged playground and landscape at Nelson Avenue Waterfront Park. | Cleveland and Nelson Avenues, Staten Island | Staten Island | 2018-10-22 |  |  | Seaside Wildlife Nature Park | Construction
RG-214MA | 846 P-5PLG13C | NA | Staten Island General Site Work (RG-214MA) | This project will reconstruct play equipment, safety surfacing, pavements, and fencing in Staten Island. | Various locations, Staten Island | Staten Island | 2018-09-05 |  | 2017-09-12 | Multisite in Staten Island | Completed
RG-216MA | 846 P-5CPIB12 | NA | Levy Playground, McDonald Park and DeMatti Playground Comfort Station Reconstruction | This project will reconstruct three comfort stations at various locations in Staten Island. | Levy Playground, 133 Jewett Ave, Staten Island; McDonald Playground, east of Broadway, between Myrtle and Forest Avenues, Staten Island; DeMatti Playground, 430 Tompkins Ave, Staten Island | Staten Island | 2018-10-24 |  |  | Multisite in Staten Island | Construction
RG-415M | 846 P-5PM14A | NA | Staten Island Shoreline Reconstruction (RG-415M) | This project will reconstruct reinforced sand berms installed following Hurricane Sandy on the eastern shorelines of Staten Island. | From South Beach to Conference House Park Beach. | Staten Island | 2018-05-01 |  |  | Multisite in Staten Island | Construction
RG-515MA1 | 846 P-5CPIBN6 | NA | Arrochar Playground and Grandview Playground Comfort Station Reconstruction | This project will reconstruct the comfort stations at various locations in Staten Island. | Arrochar Playground, Staten Island; Grandview Playground, Staten Island | Staten Island | 2018-10-17 |  |  | Multisite in Staten Island | Construction
RG-516M | 846 P-5TRE17A | NA | Staten Island Street Tree Planting FY17 | This project will plant new street trees throughout Staten Island. | Various locations, Staten Island. | Staten Island | 2018-11-06 |  |  | Multisite in Staten Island | Construction
RG-714M | 846 P-501FABB | NA | Faber Pool and Lyons Pool Boiler Repair (RG-714M) | This multisite contract will reconstruct the boilers and heating systems at Faber Pool and Lyons Pool. | Richmond Terrace between Faber Street and Sharpe Avenue; Murray Hulbert Avenue between Victory Boulevard and Hannah Street, Staten Island | Staten Island | 2018-02-28 | 2018-05-15 |  | Multisite in Staten Island | Construction
X001-207MA2 | 846 P-1CROT14 | X001A | Aqueduct Walk 182nd Street Comfort Station Construction | This project will construct a comfort station in Aqueduct Walk. | Aqueduct Avenue East between 182nd and West 183rd Streets, the Bronx | Bronx | 2018-03-12 |  |  | Aqueduct Walk | Construction
X003-114M | 846 P-1CROT36 | X003 | Pelham Parkway Malls Reconstruction | This project will reconstruct the Pelham Parkway Malls between Boston Road and Wallace Avenue in the Bronx. | Boston Road and Wallace Avenue | Bronx | 2018-03-20 |  | 2017-11-06 | Pelham Parkway | Completed
X004-113M | 846 P-1SHOEBS | X004 | Shoelace Park Green Infrastructure Construction | This project will construct green infrastructure to capture storm water and stabilize hillsides and slopes at Shoelace Park. | Bronx Boulevard between East 227th and East 228th Streets | Bronx | 2018-07-30 |  |  | Bronx River Parkway | Construction
X004-213M | 846 P-1CROT06 | X004 | Bronx River Park 233rd Street Bikeway Reconstruction | This project will reconstruct the paths, landscape and staircase located at East 233rd Street in Bronx River Park. | East 233rd Street and the Bronx River, the Bronx | Bronx | 2018-01-24 | 2018-06-22 |  | Bronx River Parkway | Construction
X028-114M | 846 P-104JKIL | X028 | Joyce Kilmer Park Perimeter Fence Construction | This project will construct a steel perimeter fence in Joyce Kilmer Park. | Grand Concourse between East 161st and East 164th Streets | Bronx | 2018-03-12 |  | 2018-03-12 | Joyce Kilmer Park | Completed
X045-116M | 846 P-101STMH | X045 | St. Mary's Recreation Center Pool and Gymnasium HVAC Reconstruction | This project will provide a heating, ventilation, air conditioning, and dehumidification system to serve the swimming pool and gymnasium, as well as ventilation upgrades throughout the building. | 450 Saint Ann's Avenue Bronx, NY 10455 Cross Streets: 145th Street and St. Ann's Avenue | Bronx | 2018-12-03 |  |  | St. Mary's Playground | Construction
X092-113M | 846 P-112DRUN | X092 | Van Cortlandt Park Dog Run Construction | This project will construct a dog run in Van Cortlandt Park. | Van Cortlandt Park East between Oneida Avenue and East 238th Street | Bronx | 2018-08-13 |  |  | Van Cortlandt Park | Construction
X092-114M | 846 P-108SKTE | X092 | Van Cortlandt Park Basketball Court and Skate Park Construction | This project will construct a basketball court and skate park in Van Cortlandt Park. | Van Cortlandt Park | Bronx | 2018-02-12 |  |  | Van Cortlandt Park | Construction
X113-115MA | 846 P-1CPIHNT | X113 | Hunts Point Playground Reconstruction | This project will reconstruct the play equipment, safety surfacing, spray shower, fencing, benches and landscaping in Hunts Point Playground. | Spofford Avenue Between Faile Street and Hunts Point Avenue | Bronx | 2018-08-27 |  |  | Hunts Point Playground | Construction
X126-106MA | 846 P-1CRO66A | X126 | Ferry Point Park West Comfort Station Construction | This project will construct a comfort station in Ferry Point Park. | Bronx Whitestone Bridge, Schley Avenue, Westchester Creek and the East River, the Bronx | Bronx | 2017-08-01 | 2018-03-12 | 2018-03-12 | Ferry Point Park | Completed
X126-206MA1 | 846 P-1CRO66B | X126 | Ferry Point Park West Comfort Station Construction - Electrical | This project will install the electrical work in connection with the construction of a comfort station at Ferry Point Park West. | Ferry Point Park West CS | Bronx | 2017-12-26 | 2018-02-19 | 2018-03-12 | Ferry Point Park | Completed
X126-306MA | 846 P-1CRO66C | X126 | Ferry Point Park West Comfort Station Construction - Plumbing | This project will install the plumbing work in connection with the construction of a comfort station at Ferry Point Park West. | Ferry Point Park West CS | Bronx | 2017-12-26 | 2018-02-23 | 2018-03-12 | Ferry Point Park | Completed
X126-406MA | 846 P-1CRO66D | X126 | Ferry Point Park West Comfort Station Construction - HVAC | This project will install the HVAC work in connection with the construction of a comfort station at Ferry Point Park West. | Ferry Point Park West CS | Bronx | 2017-12-26 | 2018-02-23 | 2018-03-12 | Ferry Point Park | Completed
X136-115M | 846 P-1CRO19 | X136 | Harris Park Reconstruction | This project will reconstruct the park's perimeter lawn area, construct four (4) sets of steel signage, and construct a storm sewer connection. | Harris Park located between Goulden and Paul Avenues and West 205th Street and Bedford Park Boulevard | Bronx | 2018-02-05 |  | 2018-02-01 | Harris Park | Completed
X169-114M | 846 P-112AGNS | X169 | Agnes Haywood Park Basketball Court Reconstruction | This project will reconstruct the sports courts and complete miscellaneous site work in Agnes Haywood Park in the Bronx. | Located on Barnes Avenue between E. 215th Street and E 216th Street in the Bronx | Bronx | 2018-07-09 |  |  | Agnes Haywood Playground | Construction
X179-112M | 846 P-102PL52 | X179 | Kelly Playground Skate Park Reconstruction | This project will construct a skate park and reconstruct the amphitheater and basketball courts in Kelly Playground (PS 52). | Avenue Saint John between Kelly and Beck Streets | Bronx | 2018-05-15 |  |  | Playground 52 LII | Construction
X179-115M | 846 P-1CPIP52 | X179 | Playground 52 Reconstruction | This project will reconstruct the play equipment, safety surface, spray shower, fence and landscaping at Playground 52. | Kelly Street Between Avenue Saint John and Leggett Street | Bronx | 2018-03-12 |  | 2018-03-12 | Playground 52 LII | Completed
X180-114M | 846 P-107WHLN | X180 | Whalen Park Reconstruction | This project will reconstruct Whalen Park in the Bronx. | Perry Avenue and East 205th Street | Bronx | 2018-06-04 |  |  | Whalen Park | Construction
X182-115M | 846 P-101MBRO | X182 | Millbrook Park Basketball and Handball Court Reconstruction | This project will reconstruct the basketball and handball courts and complete miscellaneous site work at Millbrook Park. | Mill Brook Park at Bruckner Boulevard between Cypress and St. Ann's Avenues | Bronx | 2018-06-04 |  |  | Millbrook Playground | Construction
X290-116MA | 846 P-1CPILFG | X290 | Longfellow Gardens Reconstruction | This project will reconstruct Longfellow Gardens Playground, including new play equipment, spray shower, seating, lighting, fencing, pavements and planting. | Longfellow Garden Longfellow Ave, Lowell St, East 165 St. Bronx, NY | Bronx | 2018-10-30 |  |  | Longfellow Garden | Construction
X299-116M | 846 P-1CPILCM | X299 | Little Claremont Park Playground Reconstruction | This project will reconstruct Little Claremont Park Playground. | Park Avenue and Claremont Parkway, Borough of the Bronx. | Bronx | 2018-04-27 |  |  | Little Claremont Park | Construction
X304-113M | 846 SANDY1-04 | X304 | Tiffany Street Pier Reconstruction (Hurricane Sandy) | This project will reconstruct the fishing pier that was damaged by Hurricane Sandy. | Tiffany Street pier located at East river and intersection Tiffany Street and Viele Avenue, Bronx N.Y. | Bronx | 2018-04-16 |  |  | Tiffany Street Pier | Construction
XG-116M | 846 P-1TRE17A | NA | Bronx Street Tree Planting FY17 - Community Boards 1-8 | This project will plant new trees in community boards 1-8 in the Bronx. | Various locations, in the Bronx community boards 1-8. | Bronx | 2018-10-01 | 2018-10-01 |  | Multisite in the Bronx | Construction
XG-216M | 846 P-1PNYT21 | NA | Bronx Street Tree Planting FY17 - Community Boards 9-12 | This project will plant new trees in community boards 9-12 in the Bronx. | Various locations, in the Bronx community boards 9-12 | Bronx | 2018-10-11 | 2018-10-11 |  | Multisite in the Bronx | Construction