## Scheduled Completions 2020
Parks' Contract # | FMS # | Property # | Short Description | Contract Summary | Contract Location | Borough | Construction SCD | Construction ACD | Final Inspection Date | Park Name | Contract Status
B007-118M | 846 P-211BNHT | B007 | Bensonhurst Park Playground Reconstruction | This project will reconstruct the playground, adjacent path system and sitting areas at the north end of Bensonhurst Park. | Cropsey Avenue between Bay Parkway and 21st Avenue | Brooklyn | 2020-09-07 |  |  | Bensonhurst Park | Construction
B012-117M | 846 P-208BROW | B012 | Brower Park Basketball Courts Reconstruction | This project will reconstruct the basketball courts at Brower Park. | Brooklyn Avenue and Park Place | Brooklyn | 2020-05-04 |  | 2019-11-21 | Brower Park | Completed
B057-117M | 846 P-218GERT | B057 | Marine Park Gerritsen Avenue Pedestrian Path Construction Phase 2 | This project will construct a new asphalt path, benches and accessible entrances adjacent to the Gerritsen Avenue ballfields in Marine Park. | Gerritsen Avenue near Florence Avenue and Channel Avenue | Brooklyn | 2020-06-01 |  | 2019-10-23 | Marine Park | Completed
B057-212MA | 846 P-2BRIGHM | B057 | Brigham Street New Park Construction | This project will construct a new playground to include play equipment, swings, spray shower area, hillside slide and a picnic area near Brigham Street in Marine Park. | Southeast corner of Brigham Street and Emmons Avenue | Brooklyn | 2020-05-04 |  |  | Marine Park | Construction
B068-117M | 846 P-214KNDR | B068 | Parade Ground Dog Run Construction | This project will construct a new dog run in the Parade Ground. | Southwest lawn of the police precinct, near Coney Island Avenue and Kermit Place | Brooklyn | 2020-06-15 |  |  | Parade Ground | Construction
B073-117M | 846 P-2PWBPFB | B073 | Prospect Park New Flatbush Avenue Entrances Construction and Willink Entrance Reconstruction | This project will reconstruct the Willink Entrance to Prospect Park and construct two new entrances: a new grand entrance and pedestrian bridge at the existing berm separating Flatbush Avenue from the Rose Garden, south of Grand Army Plaza, and a new minor entrance connecting Flatbush Avenue to the internal pathway east of the Dongan Oak Monument. | Flatbush Avenue between Grand Army Plaza and Empire Boulevard | Brooklyn | 2020-07-13 |  |  | Prospect Park | Construction
B073-215M | 846 P-200PPBL | B073 | Prospect Park Long Meadow Ballfields 4 and 5 Reconstruction | This project will reconstruct ballfields 4 and 5 in the Long Meadow at Prospect Park. | West Drive between 10th Street and 12th Street | Brooklyn | 2020-12-07 |  |  | Prospect Park | Construction
B073-416M | 846 P-200PPOP | B073 | Prospect Park Tea House Pavilion Reconstruction | This project will reconstruct the Tea House Pavilion in Prospect Park, including roofing and framing, drainage, new paths and stairs, handrails, and security lighting. | East Drive and Wellhouse Drive | Brooklyn | 2020-12-07 |  |  | Prospect Park | Construction
B082-116M | 846 P-210SHRD | B082 | Shore Road Park Field House Reconstruction | This project will reconstruct the field house at Shore Road Park. | 95th Street between Shore Road and Belt Parkway | Brooklyn | 2020-09-29 |  |  | Shore Park and Parkway | Construction
B087-117MA | 846 P-207SSPK | B087 | Sunset Park Path Reconstruction | This project will reconstruct stairs, handrails and landings in Sunset Park. | Near the corner of 5th Avenue and 44th Street, and at 43rd Street and 5th Avenue. | Brooklyn | 2020-10-26 |  |  | Sunset Park | Construction
B131-117M | 846 P-204RUDD | B131 | Rudd Playground Skate Park and Basketball Courts Reconstruction | This project will reconstruct the basketball courts and construct a new skate park at Rudd Playground including a new accessible ramp to connect the two levels within the park and reconstruction of pavements, stairs, fencing, benches, plantings, drainage and water supply systems, and park security lighting. | Aberdeen Street east of Bushwick Avenue | Brooklyn | 2020-07-06 |  |  | Rudd Playground | Construction
B166B-118M | 846 P-215HCPL | B166B | Homecrest Playground Reconstruction | This project will reconstruct the children's play area in Homecrest Playground, including the spray shower, play equipment, paving, site furniture, landscaping and utilities. | Williams Court, East 14th Street, Homecrest Avenue, Shore Parkway | Brooklyn | 2020-10-12 |  |  | Homecrest Playground | Construction
B167-117M | 846 P-2CPILGD | B167 | La Guardia Playground Reconstruction Phase 1 | This project will reconstruct the sports courts and plaza (southern parcel) at La Guardia Playground. | Havemeyer Street, South 5th Street, Brooklyn Queens Expressway | Brooklyn | 2020-09-26 |  |  | La Guardia Playground West | Construction
B210-116M | 846 P-210JCAR | B210W | John J Carty Park Tennis Courts Reconstruction | This project will reconstruct the tennis courts in John J. Carty Park. | East side of Fort Hamilton Parkway between Marine Avenue and 101st Street | Brooklyn | 2019-07-10 | 2020-05-31 |  | John J Carty Park | Construction
B223NC-118M | 846 P-2CPIPEN_PC-002323 | B223NC | Penn Triangle Reconstruction | This project will reconstruct Penn Triangle. | Penn Street, Wythe Avenue, Williamsburg Street East | Brooklyn | 2020-11-10 |  |  | Penn Triangle | Construction
B251-117M | 846 P-215MBGD | B251 | Manhattan Beach Dog Run Reconstruction | This project will reconstruct the existing dog run to provide separate dog runs for both small and large dogs with new surface materials, drinking fountains for both dogs and their owners, and seating at Manhattan Beach Park. | Oriental Boulevard at Kensington Street | Brooklyn | 2020-07-27 |  |  | MANHATTAN BEACH PARK | Construction
B254-117M | 846 P-209WNGE | B254 | Wingate Park Basketball Courts Reconstruction | This project will reconstruct the basketball courts at Wingate Park. | Winthrop Street between Brooklyn Avenue and Kingston Avenue | Brooklyn | 2020-10-26 |  |  | Wingate Park | Construction
B290-117M | 846 P-2PEDPLZ | B290 | Public Place Mall Paving Reconstruction | This project will reconstruct Public Place Mall. | Eldert Lane, Liberty Avenue, and Glenmore Avenue | Brooklyn | 2020-04-14 |  |  | Public Place | Construction
B324-117M | 846 P-218JFEE | B324 | Jacob Joffe Fields Playground Reconstruction | This project will reconstruct the playground at Jacob Joffe Fields. | East 58th Street and East 59th Street near Avenue L | Brooklyn | 2020-06-01 |  |  | Joffe Park | Construction
B335-116M | 846 P-218BILD | B335 | Bildersee Playground Reconstruction Phase 1 | This project will construct a new synthetic turf field and reconstruct the basketball courts at Bildersee Playground. | Flatlands Avenue between East 81st Street and East 82nd Street | Brooklyn | 2019-09-03 | 2020-02-07 | 2019-12-16 | Bildersee Playground | Completed
B339-117M | 846 P-2CPINEW | B339 | Newport Playground Comfort Station Reconstruction | This project will reconstruct the comfort station in Newport Playground. | Riverdale Avenue between Osborn Street and Thatford Avenue | Brooklyn | 2020-08-06 |  |  | Newport Playground | Construction
BG-515MA | 846 P-2SANDY | NA | Coney Island Greenstreets and Green Infrastructure Construction | This project will construct green infrastructure to capture storm water at Greenstreets at various locations near Coney Island Beach and Boardwalk. | Between Brighton 1st Street, Neptune Avenue, West End Avenue, and the Coney Island Boardwalk | Brooklyn | 2020-09-14 |  |  | Multisite in Brooklyn | Construction
BG-715MA | 846 P-2PLAY15 | NA | Brooklyn General Site Work (BG-715MA) | This project will reconstruct the play equipment, safety surfacing, handball courts, basketball courts, pavements, fencing, site plumbing and general site work at various parks in Brooklyn. | Various locations in Brooklyn. | Brooklyn | 2019-06-18 | 2020-06-17 |  | Multisite in Brooklyn | Construction
CNYG-1215MA | 846 P-6NCRC15 | NA | Citywide Nature & Recreation Centers Reconstruction (CNYG-1215MA) | This multisite contract will reconstruct nature and recreation centers citywide. | Various locations, citywide |  | 2020-02-26 |  | 2018-03-30 | Multisite Citywide | Completed
CNYG-1615MA | 846 P-6BLGC15 | NA | Citywide Buildings Reconstruction (CNYG-1615MA) | This project will perform building reconstruction work at various locations citywide. | Various locations, citywide |  | 2020-10-13 |  |  | Multisite Citywide | Construction
M014-117M | 846 P-3PWBJRP | M014 | Jackie Robinson Park Reconstruction | This project will reconstruct stairways, fencing, sidewalks, and entrances in Jackie Robinson Park. | West 145th Street, West 155th Street, Edgecombe Avenue, Bradhurst Avenue | Manhattan | 2020-01-12 |  |  | Jackie Robinson Park | Construction
M015-118M | 846 P-3COLUMB | M015 | Columbus Park Mulberry Street Entrance Reconstruction | This project will reconstruct the Mulberry Street entrance at Columbus Park. | Mulberry Street between Bayard and Mosco Streets | Manhattan | 2020-07-27 |  | 2019-10-18 | Columbus Park | Completed
M017-118M | 846 P-303CRHP | M017 | Corlears Hook Park Dog Run Reconstruction | This project will reconstruct the dog run at Corlears Hook Park, adding stable ground surface, water features and dog waste containers, and replacing fencing. | Cherry Street, Jackson Street, FDR Drive | Manhattan | 2020-10-26 |  |  | Corlears Hook Park | Construction
M037-318M | 846 P-3ANCH04_PC-002453 | M037 | Highbridge Anchor Park Reconstruction Phase I | This project will reconstruct the staircase and pathways, including pavement, drainage, lighting and planting, in Highbridge Park. | West 181st Street to Dyckman Street | Manhattan | 2020-06-22 |  |  | Highbridge Park | Construction
M047-216MA | 846 P-311TJPK | M047 | Thomas Jefferson Park Irrigation Installation | This project will install new irrigation and paths at Thomas Jefferson Park. | First Avenue between East 111th Street and East 114th Street | Manhattan | 2020-07-13 |  | 2019-09-27 | Thomas Jefferson Park | Completed
M053-118M | 846 P-307TRDR | M053 | Theodore Roosevelt Park Dog Run Reconstruction | This project will reconstruct Bull Moose Dog Run in Theodore Roosevelt Park. | West 81st Street and Central Park West | Manhattan | 2020-07-27 |  |  | Theodore Roosevelt Park | Construction
M056-118M | 846 P-309MPMP | M056 | Morningside Park Middle Playground and Basketball Courts Reconstruction | This project will reconstruct Middle Playground and the basketball courts at Morningside Park. | Morningside Drive and 118th Street | Manhattan | 2020-12-07 |  |  | Morningside Park | Construction
M058-116M | 846 P-311MGLL | M058 | Marcus Garvey Park Comfort Station Construction | This project will construct a new comfort station and Little League building in Marcus Garvey Park. | 18 Mount Morris Park West, between West 121st Street and West 122nd Street | Manhattan | 2019-01-29 | 2020-03-20 |  | Marcus Garvey Memorial Park | Construction
M065-114M | 846 P-303LGPK | M065 | Luther Gulick Park Reconstruction | This project will reconstruct Luther Gulick Park. | Delancey Street between Willett Street and Columbia Street | Manhattan | 2020-09-12 |  |  | Luther Gulick Park | Construction
M071-115MA | 846 P-3RVSSCA | M071 | Riverside Park 109th Street Skate Park Reconstruction | This project will reconstruct the existing skate park with new skate elements, fencing, benches, picnic tables, and landscaping at West 109th Street in Riverside Park. | Between Henry Hudson Parkway and Riverside Drive at West 109th Street | Manhattan | 2020-05-04 |  |  | Riverside Park | Construction
M071-213M | 846 P-309RBUS | M071 | Riverside Drive Bus Stop and Safety Measure Installation | This project will reconstruct the bus stops and perimeter sidewalks along Riverside Drive. | Riverside Drive between West 97th Street and West 125th Street | Manhattan | 2020-05-31 |  |  | Riverside Park | Construction
M081-116M | 846 P-308CSPG | M081 | Carl Schurz Park Playground Reconstruction | This project will reconstruct the children's playground in Carl Schurz Park. | East End Avenue from Gracie Square to East 86th Street | Manhattan | 2020-09-01 |  |  | Carl Schurz Park | Construction
M104-117M | 846 P-6PRKLOT | M104 | 5 Boro Complex and Garage Parking Lot Reconstruction | This project will reconstruct the parking lot at the 5 Boro Complex and Garage on Randall's Island. | 20 Bronx Shore Road | Manhattan | 2020-07-20 |  |  | Randall's Island | Construction
M105-117M | 846 P-303SDRB | M105 | Sara D. Roosevelt Park Comfort Station Reconstruction | This project will reconstruct a comfort station in Building A in Sara D Roosevelt Park. | Stanton Street between Chrystie Street and Forsyth Street | Manhattan | 2020-01-27 |  |  | Sara D. Roosevelt Park | Construction
M107-116M | 846 P-311HEL3 | M107 | Hell Gate Pathway Construction Phase 3 | This project will construct a multi use pedestrian pathway under the Amtrak Viaduct at Wards Island Park. | Under the Amtrak Viaduct from Hell Gate Bridge to Column 27 and Central Road | Manhattan | 2020-05-30 |  |  | Wards Island | Construction
M107-118M | 846 P-3RNDLOT_PC-002632 | M104 | Randall's Island PEP Academy Complex Reconstruction | This project will reconstruct the parking lot at the Randall's Island Parks Enforcement Patrol (PEP) Academy Complex. | Hell Gate Circle between Sunken Meadow Loop and Rivers Edge Road, under the Robert F. Kennedy Triborough Bridge | Manhattan | 2020-07-06 |  |  | Randall's Island | Construction
M113-118M | 846 P-3CPISUR | M113 | Joseph Sauer Park Reconstruction | This project will reconstruct Joseph Sauer Park. | East 12th Street between Avenue A & Avenue B | Manhattan | 2020-10-19 |  |  | Joseph C. Sauer Plgd | Construction
M138-118M | 846 P-3CPIBBJ | M138 | Bill 'Bojangles' Robinson Playground Reconstruction | This project will reconstruct Bill 'Bojangles' Robinson Playground. | West 150th Street between Frederick Douglass Boulevard and Adam Clayton Powell Jr. Boulevard | Manhattan | 2020-10-26 |  |  | Playground (Bill Robinson) | Construction
M165A-116M | 846 P-303BPCS | M165 | Baruch Playground Comfort Station Reconstruction | This project will reconstruct the comfort station at Baruch Playground. | Baruch Place and Rivington Street | Manhattan | 2020-01-27 |  |  | Baruch Playground | Construction
M196-118M | 846 P-3CPIPGI | M196 | Playground One Reconstruction | This project will reconstruct Playground One. | Madison Street between Oliver Street and Catherine Street | Manhattan | 2020-07-06 |  |  | PS 1 Playground (Alfred Smith) | Construction
M223-116M | 846 P-309JSPL | M223 | Jacob H. Schiff Playground Basketball and Handball Courts Reconstruction | This project will reconstruct basketball and handball courts at Jacob H. Schiff Playground. | Amsterdam Avenue Between 136th Street and 138th Street | Manhattan | 2020-08-24 |  |  | Jacob H. Schiff Playground | Construction
M240-118M | 846 P-3CPI3AP_PC-002238 | M240 | Audubon Playground Reconstruction | This project will reconstruct Audubon Playground. | Audubon Avenue between West 169th Street and West 170th Street | Manhattan | 2020-04-27 |  |  | Audubon Playground | Construction
M260-114M | 846 P-304CRLB | M260 | Chelsea Recreation Center Locker Room Reconstruction | This project will reconstruct the men's and women's locker rooms at the Chelsea Recreation Center. | 430 West 25th Street | Manhattan | 2020-03-18 |  |  | Chelsea Recreation Center | Construction
M385-118M | 846 P-3DELURY | M385 | DeLury Square Reconstruction | This project will reconstruct DeLury Square. | Fulton Street between Gold and Cliff Streets | Manhattan | 2020-11-05 |  |  | DeLury Square | Construction
MG-114M | 846 SANDY3-13 | NA | Riverside Park and Fort Washington Park Pathway Reconstruction (Hurricane Sandy) | This project will reconstruct paths, pavements, and general site work in Riverside Park South, Riverside Park and Fort Washington Park in Manhattan, which were damaged by Hurricane Sandy. | Hudson River shoreline in Riverside Park South, Riverside Park and Fort Washington Park, Manhattan | Manhattan | 2020-10-19 |  |  | Multisite in Manhattan | Construction
MG-318M | 846 P-3RIVJOA | NA | Joan of Arc Park Reconstruction and Riverside Park Adult Fitness Equipment Installation | This project will reconstruct the concrete stairs and asphalt paths in Joan of Arc Park, and install adult fitness equipment, bike racks and benches adjacent to the basketball courts at Neufeld Playground near West 76th Street in Riverside Park. | Joan of Arc Park: Riverside Drive from West 91st Street to West 95th Street. Riverside Park: West 76th Street, south of Neufeld Playground | Manhattan | 2020-04-27 |  | 2019-10-21 | Multisite in Manhattan | Completed
MG-41300-114M | 846 P-301EPPK | MZ25 | Elizabeth H. Berger Plaza Construction | This project will construct Elizabeth H. Berger Plaza, closing the slip road between two smaller parks to create one larger plaza with plantings, a lawn mound, and seating. | Trinity Place, Greenwich Street, Morris Street and Egdar Street | Manhattan | 2020-08-10 |  |  | Greenstreet | Construction
MG-41350-115M | 846 P-304LRSQ | MZ06 | Little Red Square Reconstruction | This project will reconstruct Little Red Square with new pavements, curb alignments, seating, and plantings. | 6th Avenue between Bleecker Street and West Houston Street | Manhattan | 2020-03-03 |  |  | Little Red Square | Construction
MG-815M | 846 P-307BMAP | NA | Broadway Malls Reconstruction | This project will reconstruct landscapes, pavements, fences and benches at several malls along Broadway from West 102nd to 104th Streets and from West 137th to 139th Streets. | West 102nd to 104th Streets and West 137th to 139th Streets | Manhattan | 2019-08-12 | 2020-06-29 |  | Multisite in Manhattan | Construction
Q004-218M | 846 P-4ANCH02_Q004-218M | Q004 | Astoria Park Track and Field Reconstruction | This project will reconstruct the track and field in Astoria Park. | Shore Boulevard, RFK Bridge, 18th Street, Astoria Park South | Queens | 2020-05-18 |  | 2019-10-18 | Astoria Park | Completed
Q008-117M | 846 P-413BRO3 | Q008 | Brookville Park Entrance Reconstruction | This project will reconstruct an entrance to Brookville Park. | 147th Avenue and Brookville Boulevard | Queens | 2020-07-07 |  |  | Brookville Park | Construction
Q012-117M | 846 P-4CROCLL | Q012 | Crocheron Park Little League Ballfields Reconstruction | This project will reconstruct the ballfields at Crocheron Park. | Between Cross Island Parkway, Corbett Road, and 214th Place | Queens | 2020-07-06 |  |  | Crocheron Park | Construction
Q020-216M | 846 NDF-HLND | Q020 | Highland Park Lower Western Playground Reconstruction | This project will reconstruct Lower Western Playground in Highland Park. | Jamaica Avenue Between Elton Street and Cleveland Street | Queens | 2019-07-08 | 2020-04-30 |  | Highland Park | Construction
Q026-118M | 846 P-4LINDE2 | Q026 | Park of the Americas Synthetic Turf and Playground Reconstruction | This project will reconstruct the playground, spray shower and synthetic turf field at Park of the Americas. | 41st Avenue, 103rd Street, 42nd Avenue, 104th Street | Queens | 2020-08-03 |  |  | Park Of The Americas | Construction
Q066H-118M | 846 P-4CPICHP | Q066H | Chappetto Square Reconstruction | This project will reconstruct Chappetto Square. | Hoyt Avenue North, 21st Street, 23rd Street, and 24th Drive | Queens | 2020-08-17 |  |  | Chappeto Square | Construction
Q099-117M | 846 P-415FOTF | Q099 | Flushing Meadows Corona Park Fountain of the Fairs Reconstruction | This project will reconstruct and provide for the adaptive re-use of the Reflecting Pool in Flushing Meadows Corona Park. | Between Unisphere and Fountain of the Planets | Queens | 2020-09-07 |  |  | Flushing Meadows Park | Construction
Q099-317M | 846 P-4PWOB01 | Q099 | Flushing Meadows Corona Park Henry Hudson Entrance Reconstruction | This project will reconstruct the Henry Hudson entrance at Flushing Meadows Corona Park. | 111th Street between 53rd Avenue and 56th Avenue | Queens | 2020-05-26 |  |  | Flushing Meadows Park | Construction
Q099-808MA1 | 846 P-4OLMST4 | Q099 | Olmsted Center Reconstruction | This project will reconstruct the Olmsted Center in Flushing Meadows Corona Park. | 117-02 Roosevelt Avenue | Queens | 2016-10-31 | 2020-09-18 |  | Flushing Meadows Park | Construction
Q099-917M | 846 P-4FMMAUR | Q099 | Flushing Meadows Corona Park Mauro Playground Reconstruction | This project will reconstruct Mauro Playground in Flushing Meadows Corona Park. | Park Drive East at 73rd Terrace | Queens | 2020-10-24 |  | 2019-11-26 | Flushing Meadows Park | Completed
Q104-114M | 846 P-401QSE2 | Q104 | Queensbridge Park Field House Construction | This project will construct a field house in Queensbridge Park. | Vernon Boulevard between the Queensboro Bridge and 41st Avenue | Queens | 2019-07-23 | 2020-01-31 |  | Queensbridge Park | Construction
Q163-111MA | 846 P-414RKSP | Q163 | Rockaway Beach Skate Park Reconstruction | This project will reconstruct the skate park at Rockaway Beach. | Shore Front Parkway between Beach 91st Street and Beach 92nd Street | Queens | 2020-12-01 |  |  | Rockaway Beach & Boardwalk | Construction
Q163-315M | 846 P-414RBHD | Q163 | Rockaway Beach Shore Front Parkway Handball Courts Reconstruction | This project will reconstruct the handball courts at Rockaway Beach. | Shore Front Parkway between Beach 102nd Street and Beach 105th Street | Queens | 2020-03-09 |  |  | Rockaway Beach Boardwalk | Construction
Q218-216M | 846 P-4DUTCH1 | Q218 | Dutch Kills Playground Comfort Station Reconstruction | This project will reconstruct the comfort station at Dutch Kills Playground. | Crescent Street, 28th Street, 36th Avenue, 37th Avenue | Queens | 2020-01-14 |  | 2019-12-12 | Dutch Kills Playground | Completed
Q220B-118M | 846 P-412NOR2_PC-002292 | Q220B | Norelli Hargreaves Playground Basketball Courts and Multi-Purpose Play Area Reconstruction | This project will install new basketball courts and a multi-purpose play area at Norelli-Hargreaves Playground. | Van Wyck Expressway, 142nd Street, 106th Avenue | Queens | 2020-08-03 |  |  | Norelli-Hargreaves Playground | Construction
Q226-117M | 846 P-4HCOVPG | Q226 | Hallets Cove Playground Reconstruction | This project will reconstruct Hallets Cove Playground. | Vernon Boulevard between Main Avenue and Astoria Boulevard | Queens | 2020-02-24 |  | 2019-12-30 | Hallets Cove Plgd | Completed
Q293-118M | 846 P-411SWP2 | Q293 | Saul Weprin Playground Plaza Reconstruction | This project will reconstruct the pavements, seating, and fencing at the plaza in Saul Weprin Playground. | 56th Avenue between 201st Street and 202nd Street | Queens | 2020-04-13 |  |  | Saul Weprin Playground | Construction
Q296-116M | 846 P-4CPIP35 | Q296 | Playground Thirty Five XXXV Reconstruction | This project will reconstruct Playground Thirty Five XXXV. | 35th Avenue between Steinway Street and 41st Street | Queens | 2019-05-20 | 2020-01-31 | 2019-12-30 | 35 Playground | Completed
Q303-117M | 846 P-403TTOT | Q303 | Travers Park Tot Lot Reconstruction | The project will reconstruct the tot lot in Travers Park. | 78th Street between Northern Boulevard and 34th Avenue | Queens | 2020-08-10 |  |  | Travers Park | Construction
Q361-115M | 846 P-404CCPS | Q361 | Clement Clarke Moore Homestead Playground Reconstruction | This project will reconstruct the playground, spray shower, and pavements at Clement Clarke Moore Playground. | Broadway, 45th Avenue, 82nd Street | Queens | 2020-03-16 |  |  | Moore Homestead Playground | Construction
Q373-112MA2 | 846 P-4031272 | Q373 | East Elmhurst Playground Reconstruction | This project will reconstruct the playground and handball courts at PS 127 (East Elmhurst) Playground. | 25th Avenue between 98th Street and 100th Street | Queens | 2020-03-16 |  |  | East Elmhurst Playground (PS 127) | Construction
Q392-210MA | 846 P-413IDPK | Q392 | Idlewild Park Nature Center Construction | This project will construct a nature center in Idlewild Park. | 149th Avenue and Springfield Lane | Queens | 2020-02-25 |  |  | Idlewild Park | Construction
Q398-117M | 846 P-4RDGEWD | Q398 | Rosemary's Playground Reconstruction | This project will reconstruct the playground and spray shower at Rosemary's Playground. | Woodward Avenue between Madison Street and Woodbine Street | Queens | 2020-06-01 |  |  | JHS 93 Plgd (Ridgewood) | Construction
Q443-117M | 846 P-4CPIALM | Q443 | Almeda Playground Reconstruction | This project will reconstruct Almeda Playground. | Beach Channel Drive between Beach 65th Street and Beach 66th Street | Queens | 2020-09-22 |  |  | Almeda Playground (PS 42) | Construction
Q448-118M | 846 P-4BWIDEQ | Q448 | Roy Wilkins Park Performance Area Reconstruction | This project will reconstruct the performance area at Roy Wilkins Park. | Merrick Boulevard between 119th Avenue and Victoria Road | Queens | 2020-01-21 |  | 2019-05-08 | Roy Wilkins Recreation Center | Completed
QG-116MA | 846 P-408BRIA | NA | Briarwood Playground and Phil 'Scooter' Rizzuto Park Playground Reconstruction | This project will reconstruct the playgrounds at Briarwood Playground and Phil 'Scooter' Rizzuto Park. | Various locations in Queens | Queens | 2020-03-03 |  |  | Multisite in Queens | Construction
QG-618M | 846 P-4BWIDER_PC-002329 | NA | Queens Adult Fitness Equipment Construction (QG-618M) | This project will install adult fitness equipment at Cambria Playground, Haggerty Park, and Montbellier Park. | Various locations in Queens | Queens | 2020-07-27 |  |  | Multisite in Queens | Construction
R008-117M | 846 P-501FABL | R008 | Faber Park Active Recreation, Lighting and Seating Area Construction | This project will construct new active recreation areas, paths, seating, lighting and an expanded public gathering area at Faber Park. | 2175 Richmond Terrace, between Faber Street and Sharpe Avenue | Staten Island | 2020-10-15 |  |  | Faber Park | Construction
R017-115M | 846 P-5FRESH9 | R017 | Freshkills North Park Pathway and Comfort Station Construction | This project will construct a new multi-use pathway, overlook structures, and comfort station with composting toilets in the northern section of Freshkills Park. | Dean Avenue, West Shore Expressway, Fresh Kills and Main Creek | Staten Island | 2020-01-05 | 2021-04-30 |  | Fresh Kills Park | Construction
R061-116M | 846 P-5CPISTP | R061 | Stapleton Playground Reconstruction | This project will reconstruct the playground, multi-use fields, basketball and handball courts, and water features at Stapleton Playground. | Tompkins Avenue between Broad and Hill Streets | Staten Island | 2020-03-20 |  |  | Stapleton Playground | Construction
R067-117M | 846 SANDY5-45 | R067 | MacArthur Park Multi-Purpose Ballfield and Basketball Court Reconstruction | This project will reconstruct the existing ballfields, basketball courts, and sports lighting, and improve the edges and entrances at MacArthur Park. | Jefferson Street between Dongan Hills Avenue and Seaver Avenue | Staten Island | 2020-10-13 |  |  | MacArthur Park | Construction
R135-113MA | 846 P-503CRBP | R135 | Crescent Beach Park Landscape Improvement and Pathway Construction | This project will construct new paths, seating and a tot lot and reconstruct the landscape at Crescent Beach Park. | Tennyson Drive between Armstrong and Wiman Avenues | Staten Island | 2019-04-22 | 2020-01-30 |  | Crescent Beach Park | Construction
R153-118M | 846 SANDY5-50_PC-002219 | R153 | Fairview Park Multi-Purpose Field and Landscape Construction | This project will construct a multi-purpose field, baseball field, tennis courts, pickleball courts, adult fitness equipment, picnic area, parking area, bio-retention areas, paths, and landscape elements at Fairview Park. | Arthur Kill Road and Veterans Road West | Staten Island | 2020-08-04 |  |  | Fairview Park | Construction
RG-315MA1 | 846 P-5PLG15B | NA | Staten Island General Site Work (RG-315MA1) | This project will reconstruct play equipment, pavements, fencing, water supply, drainage, site features, and plantings at various parks in Staten Island. | Various locations in Staten Island | Staten Island | 2020-03-21 | 2020-03-21 |  | Multisite in Staten Island | Construction
X002-117M | 846 P-1BXPFIT_PC-002206 | X002 | Bronx Park Adult Fitness Equipment Construction | This project will construct an adult fitness area in Bronx Park. | Bronx Park East between Arnow Avenue and Britton Street | The Bronx | 2020-03-23 |  | 2019-07-05 | Bronx Park | Completed
X010-114M | 846 P-1CRNAPK | X010 | Crotona Park Nature Center Reconstruction | This project will reconstruct the nature center in Crotona Park. | Crotona Avenue and Crotona Park East | The Bronx | 2019-09-09 | 2020-04-17 |  | Crotona Park | Construction
X033-118M | 846 P-107KOSS | X033 | Kossuth Playground Reconstruction | This project will reconstruct Kossuth Playground in Mosholu Parkway to include new play equipment, spray shower features, basketball courts, fencing, pavement, benches, lighting and plantings. | East Mosholu Parkway North between Kossuth Avenue and Steuben Avenue | The Bronx | 2020-10-19 |  |  | Mosholu Parkway | Construction
X039-116M | 846 P-1PELSHO | X039 | Pelham Bay Park Natural Shoreline Reconstruction | This project will remove intrusive infrastructure from the natural rocky shore of Pelham Bay Park, restore coastal habitats, and improve public access to the scenic bay. | Along the waterfront between Pelham Bay Landfill and Watt Avenue | The Bronx | 2020-09-21 |  |  | Pelham Bay Park | Construction
X039-118M | 846 P-100PBSG_PC-002244 | X039 | Pelham Bay Park Sensory Garden Construction | This project will construct a barrier-free participatory garden that engages all the senses in enjoying the outdoors in Pelham Bay Park. | Bruckner Boulevard and Middletown Road next to Playground For All Children | The Bronx | 2020-08-17 |  |  | Pelham Bay Park | Construction
X092-114MD | 846 P-108SKTE_PC-002997 | X092 | Van Cortlandt Park Skate Park Construction | This project will construct a skate park in Van Cortlandt Park. | Broadway and Van Cortlandt Park South | The Bronx | 2020-06-01 |  |  | Van Cortlandt Park | Construction
X092-115M | 846 P-108VCBD | X092 | Van Cortlandt Park Playground Construction | This project will construct a playground in Van Cortlandt Park. | Broadway and Mosholu Avenue | The Bronx | 2020-05-11 |  |  | Van Cortlandt Park | Construction
X092-217M | 846 P-111VCPE | X092 | Van Cortlandt Park Broadway Entrance Reconstruction | This project will reconstruct the entrance to Van Cortlandt Park at Broadway and West 242nd Street. | Broadway at West 242nd Street | The Bronx | 2020-06-24 |  |  | Van Cortlandt Park | Construction
X092-508M | 846 P-1PUTNAM | X092 | Van Cortlandt Park Putnam Greenway Construction | This project will construct a portion of the Putnam Greenway in Van Cortlandt Park. | City line to Van Cortlandt Park South | The Bronx | 2020-08-13 |  |  | Van Cortlandt Park | Construction
X106-117M | 846 P-1CPIGAR | X106 | Garrison Playground Reconstruction | This project will reconstruct the seating area and playground at Garrison Playground. | Grand Concourse between East 144th Street and East 149th Street | The Bronx | 2020-04-28 |  |  | Garrison Playground | Construction
X111-114M | 846 P-100CDAR | X111 | Cedar Playground Comfort Station Reconstruction | This project will reconstruct the comfort station in Cedar Playground. | Cedar Avenue between West 179th Street and Sedgwick Avenue | The Bronx | 2020-01-07 |  |  | Cedar Playground | Construction
X122-117M | 846 P-111LPFE | X122 | Colucci Playground Adult Fitness Equipment Construction | This project will construct an adult fitness area in Colucci Playground. | Wilkins Avenue between Hutchinson River Parkway East and Mayflower Avenue | The Bronx | 2020-05-11 |  |  | Colucci Playground | Construction
X155-116M | 846 P-1PTSNPK | X155 | Patterson Playground Reconstruction | This project will reconstruct the playground and basketball courts at Patterson Playground. | East 145th Street, Morris and Bronx Avenues. | The Bronx | 2020-06-01 |  |  | Patterson Playground | Construction
X159-118M | P-1CPIBR2_PC-002228 | X159 | Playground 174 Play Area Reconstruction | This project will reconstruct play and adult fitness equipment, swings, spray shower, pavements, fencing, lighting, and mini-pool. | East 174th Street between Bronx River Avenue and Manor Avenue. | The Bronx | 2020-01-26 |  |  | 174th Street Playground | Construction
X271-115M | 846 P-104GPPV | X271 | Grant Park Playground and Basketball Court Reconstruction | This project will reconstruct of the playground and basketball court at Grant Park. | Northwest Corner of the intersection of Grant Avenue and East 169th Street | The Bronx | 2020-02-17 |  |  | Grant Park | Construction
X288-114M | 846 P-1TRAILX | X288 | West Farms Park Construction | This project will construct West Farms Park. | Along the western bank of the Bronx River between East Tremont Avenue and East 180th Street | The Bronx | 2020-03-30 |  |  | West Farms Rapids | Construction
X289-118M | P-106MAPE_PC-002218 | X289 | Mapes Ballfield Reconstruction | This project will reconstruct Mapes Ballfield with a new natural turf outfield, recreational sports lighting, play equipment, and adult fitness equipment. | Mapes Avenue and Prospect Avenue between East 180th Street and East 181st Street | The Bronx | 2020-11-02 |  |  | Mapes Avenue Ballfield | Construction